## README
Getaway Collective · Build State
Generated 1 Aug 2026 from the repository at C:\gc-app, commit d58044a
WHAT THIS IS | Every addressable surface, pop-up, notification and email in the platform, with what is built, what is not, and what is waiting on you. The Domain sheet carries the constitutional model: the LLP at the apex, Space / Time / Capital beneath it, Governance as the operating law.
HOW IT WAS MADE | The IA sheet is EXTRACTED, not typed. constants/routes.ts is imported directly and each row's status is read from the generated page file on disk — so this workbook cannot disagree with the application about what exists.
THE SOURCE COLUMN | The single most important column on every sheet after IA. It separates fact from opinion:
Code | Extracted from the repository. Verifiable — the file and line are named.
Doc | Stated in a repository document (WAVE-5-OPEN-QUESTIONS.md, WAVE-6-CHANGELOG.md).
Proposed | MY RECOMMENDATION. Not in the repo, not agreed by you, and not built. Nothing marked Proposed has been decided.
STATUS VALUES
Built | Renders the real interface.
Scaffold | Renders the registry Surface: the assembly's declared sections and rules, not the product. It is deliberately obvious that it is a scaffold — a scaffold that looks finished gets signed off.
Not built | Nothing exists.
Framework | Handled by a Next.js convention file rather than a page (/404 → not-found.tsx).
CELLS YOU EDIT | Yellow. They are on the Decisions and Assets sheets — the Decision / Owner / Due / Status columns. Everything else is derived and will be overwritten when this is regenerated.
WHAT IS NOT HERE | Database, authentication and payments. None of the three exists — every page reads static TypeScript. See the Gaps sheet.

## Summary
Build State · Summary
Every figure is a COUNTIF against the IA sheet. Re-derive by regenerating IA; nothing here is typed.
BY STATUS |  |  | Scaffold = renders the registry Surface, which shows the assembly's declared sections and rules. It is the product's outline, not the product.
| Count | % of total
Built | 51 | 37.78%
Scaffold | 82 | 60.74%
Framework | 2 | 1.481%
Not built | 0 | 0%
Total | 135 | 100%
BY ACCESS |  |  | Access is DERIVED from the assembly's vantage, not declared per route. Twelve routes override it, and route-lint refuses an override without a stated reason.
| Count | % of total
public | 51 | 37.78%
identified | 18 | 13.33%
accredited | 3 | 2.222%
member | 26 | 19.26%
office | 37 | 27.41%
Total | 135 | 100%
BY GROUP
| Count | % of total
gateway | 37 | 27.41%
space | 7 | 5.185%
capital | 18 | 13.33%
time | 2 | 1.481%
member | 42 | 31.11%
admin | 29 | 21.48%
Total | 135 | 100%
CROSS-CUT
Public AND built | 41 |  | What a stranger can actually see today.
Public AND scaffold | 8 |  | Public URLs that render an outline. These are indexable — the highest-priority build queue.
Indexable | 51 |  | Must equal the public count: route-lint refuses an indexable route that is not public.
Office routes with rights | 37 |  | Office routes naming a required right from lib/authority.ts.
Dynamic routes | 29 |  | Carry at least one [param] segment.
Access overrides | 27 |  | Each states its reason on the IA sheet.
OTHER SHEETS
Pop-ups built | 2
Pop-ups deliberately none | 1
Pop-ups to build | 7
Notifications firing today | 1
Notifications to build | 16
Emails live | 2
Emails to build | 16
Open gaps | 18
Decisions awaiting you | 19
Assets outstanding | 24
Domain constituents | 76
— backed by ratified object/field | 25
— derived or executable law | 10
— registered gaps (§33 queue) | 38
— out of scope by direction | 3

## IA
Information Architecture
Every URL in the system. Extracted from constants/routes.ts; Status read from the generated page file on disk. Nothing else in the platform holds a URL — a path not on this sheet does not exist.
Path | Name | Group | Vantage | Access | Indexable | Assembly | Assembly Name | Status | Rendered By | Module | Rights | Params | Access Override — why | Notes
/ | Home | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Root | publicpages |  |  |  | Hero region, then routes into the collection. No figure above the fold.
/403 | Not Permitted | gateway | gateway | public | yes | AS-16 | Signal Lost | Scaffold | Surface (registry scaffold) |  |  |  |  | Says the viewer may not see it. Never says whether it EXISTS — that distinction leaks the shape of the system to anyone probing it.
/404 | Not Found | gateway | gateway | public | yes | AS-16 | Signal Lost | Framework | [5 empty] | No stack trace, no exception name, no auto-redirect. [extract] No page.tsx: Next.js serves this from app/not-found.tsx / app/error.tsx by convention.
/500 | System Error | gateway | gateway | public | yes | AS-16 | Signal Lost | Framework | [5 empty] | [extract] No page.tsx: Next.js serves this from app/not-found.tsx / app/error.tsx by convention.
/answers | Answers | gateway | gateway | public | yes | AS-17 | The Knowledge Base | Built | Answers | gatewaypages
/auth/sign-in | Identify | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Identify | publicpages |  |  |  | No password is ever handled by the design system. Delegated.
/auth/sign-out | Sign Out | gateway | gateway | public | yes |  |  | Scaffold | Surface (registry scaffold)
/auth/verify | Verify | gateway | gateway | public | yes |  |  | Scaffold | Surface (registry scaffold) |  |  |  |  | The token arrives as a QUERY parameter, not a path segment, and it is not declared as a param for that reason. It is in the URL at all only because an email link has no other carrier — so it is single-use, short-lived, and stripped from the address bar on arrival. A URL is written to server logs, browser history and referrer headers.
/collection | The Collection | gateway | gateway | public | yes | AS-01 | The Gateway Grid | Built | GatewayGrid | gateway
/collective/gallery | The Evidence Portfolio | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Evidence | publicpages |  |  |  | PUB.08. Ships empty: every plate must say whether it is a photograph, a render or a drawing, and a portfolio of renders shown as photographs is the commonest misrepresentation in this industry. /gallery (AS-09) is a property gallery and is a different thing; both are retained.
/collective/operators | The Operators | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Operators | publicpages |  |  |  | PUB.06 — what runs a property, and who is accountable when it does not.
/collective/partners | The Foundation | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Partners | publicpages |  |  |  | PUB.05 — the independent firms. Ships with functions stated and holders withheld until each engagement is recorded against the vehicle it serves.
/collective/press | The Wire | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Wire | publicpages |  |  |  | PUB.10 — external coverage. Ships empty and says so; the wireframe's six clippings were quotes attributed to real publications that have not published them.
/communique/request | Request the Dossier | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Dossier | publicpages |  |  |  | PUB.07 — the intelligence pack. What requesting it creates is stated above the form.
/gallery | Gallery | gateway | gateway | public | yes | AS-09 | The Gallery Frame | Built | Gallery | gatewaypages
/how-it-works | How It Works | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | HowItWorks | publicpages |  |  |  | PUB.02 / PUB.11 — the doctrine, then a hard cut to the arithmetic. Distinct from /how-capital-works, which is the waterfall itself rather than the argument for it.
/journal | The Journal | gateway | gateway | public | yes | AS-30 | The Journal | Built | JournalIndex | documents |  |  |  | Index. Entries newest first; the order is checked at load.
/journal/[slug] | Journal Entry | gateway | gateway | public | yes | AS-30 | The Journal | Built | JournalEntry | documents |  | slug |  | One entry. Figures are read from the registries, never typed into the prose.
/legal | Legal | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | DocumentIndex | documents |  |  |  | Index of the standing documents.
/legal/accessibility | Accessibility Statement | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents |  |  |  | States what has been tested and what has not. Currently: contrast computed, no assistive-technology testing performed.
/legal/complaints | Complaints Procedure | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents
/legal/cookies | Cookie Notice | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents
/legal/disclosures | Standing Disclosures | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents |  |  |  | Capital at risk, past performance, no guarantee. Body size, reading tone.
/legal/privacy | Privacy Notice | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents
/legal/terms | Terms and Conditions | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents
/maintenance | Maintenance | gateway | gateway | public | yes | AS-15 | System Status | Scaffold | Surface (registry scaffold)
/portfolio | The Portfolio | gateway | gateway | public | yes | AS-07 | The Portfolio Narrative | Built | Portfolio | gatewaypages
/roles | Open Roles | gateway | gateway | public | yes | AS-18 | Recruitment | Built | Roles | gatewaypages
/roles/[code] | Role | gateway | gateway | public | yes | AS-18 | Recruitment | Built | RoleDetail | gatewaypages |  | code
/search | Search | gateway | gateway | identified | no |  |  | Scaffold | Surface (registry scaffold) |  |  |  | Results are scoped to what the viewer may see, which requires knowing who they are. An anonymous search would either return nothing or leak the index.
/signal | The Signal | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Signal | publicpages |  |  |  | PUB.09 — the weekly transmission. No tuner gate; the form is simply present.
/space | Space | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Space | publicpages |  |  |  | The physical product: what is built, from what, and what it takes to keep standing.
/status | System Status | gateway | gateway | public | yes | AS-15 | System Status | Scaffold | Surface (registry scaffold)
/story | Story | gateway | gateway | public | yes | AS-08 | The Story Playback | Built | Story | gatewaypages
/structure | The Vehicle | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Structure | publicpages |  |  |  | From the PUB.01 footer, which calls it SPV Structure. The constitutional default is an LLP; an SPV needs Board approval per property, and the page says so.
/time | Time | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Time | publicpages |  |  |  | Entitlement: what it is, what it is not, and when it begins. The wireframe's exchange console is stated as unbuilt rather than described as though it exists.
/voices | Voices | gateway | gateway | public | yes | AS-24 | Testimonials | Built | Testimonials | gateway |  |  |  | Testimonials. No figure, no return, no performance reference — regulated speech.
/collection/[property] | Property | space | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property
/collection/[property]/capital | Capital | space | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property |  | The Capital LENS at the space vantage. Renders AP-03 and routes to the console; it does not render console disclosure because a tab is labelled Capital.
/collection/[property]/gallery | Gallery | space | space | public | yes | AS-10 | The Gallery Strip | Scaffold | Surface (registry scaffold) |  |  | property
/collection/[property]/location | Location | space | space | public | yes | AS-12 | Location Intelligence | Scaffold | Surface (registry scaffold) |  |  | property
/collection/[property]/space | Space | space | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property
/collection/[property]/time | Time | space | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property
/flow | SlowSpace Coastal | space | space | public | yes |  |  | Built | Offering | flow |  |  |  | Step 1 of 5. The offering at the space vantage: capital stack, six-stage waterfall, governance and programme, each carrying its confidence class.
/capital | Capital Console | capital | capital | office | no | AS-02 | The Property Console | Scaffold | Surface (registry scaffold) |  | portfolio.manage
/capital/calls | Capital Calls | capital | member | member | no | AS-26 | The Capital Call | Scaffold | Surface (registry scaffold) |  | capital.call
/capital/distributions | Distributions | capital | capital | office | no | AS-02 | The Property Console | Scaffold | Surface (registry scaffold) |  | distribution.execute
/capital/distributions/[ref] | Distribution | capital | capital | office | no | AS-02 | The Property Console | Scaffold | Surface (registry scaffold) |  | distribution.execute | ref
/capital/offerings | Offerings | capital | capital | office | no | AS-02 | The Property Console | Scaffold | Surface (registry scaffold) |  | offering.open
/capital/properties | Properties | capital | capital | office | no | AS-02 | The Property Console | Scaffold | Surface (registry scaffold) |  | portfolio.manage
/capital/properties/[id] | Property Console | capital | capital | office | no | AS-02 | The Property Console | Scaffold | Surface (registry scaffold) |  | portfolio.manage | id
/capital/properties/[id]/programme | Programme | capital | capital | office | no | AS-11 | The Stage Progression | Scaffold | Surface (registry scaffold) |  | property.advance_lifecycle | id
/capital/properties/[id]/valuations | Valuations | capital | capital | office | no | AS-02 | The Property Console | Scaffold | Surface (registry scaffold) |  | valuation.record | id
/capital/risk | Risk Register | capital | capital | office | no | AS-28 | The Risk Register | Scaffold | Surface (registry scaffold) |  | compliance.record
/capital/waterfall | Waterfall | capital | capital | office | no | AS-04 | The Capital Explainer | Built | CapitalExplainer | gateway | distribution.execute
/commit/[offering] | Commit | capital | capital | accredited | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  | offering | An Investor commits BEFORE membership exists — the Member Law fires on settlement, not here. Requiring member access would make it unreachable by anyone who could use it.
/commit/[offering]/execute | Execute | capital | capital | accredited | no | AS-19 | The Ledger Lock | Scaffold | Surface (registry scaffold) |  |  | offering | The execution sequence for a commitment made before membership exists.
/commit/[offering]/risk | Risk Disclosure | capital | capital | accredited | no | AS-14 | The Risk Disclosure | Scaffold | Surface (registry scaffold) |  |  | offering | The gate immediately before commitment, on the same path and for the same reason.
/flow/commit | Commit | capital | capital | public | yes |  |  | Built | Commit | flow |  |  | A worked demonstration of the whole arc, on illustrative data for a fictional partner rather than a real position. Public because the point is that a prospective investor can see every step - including the accreditation and disclosure they would meet later - before committing to any of it. | Step 4. The piston, 3000ms linear. States Committed, never Member.
/flow/risk | Risk Disclosure | capital | capital | public | yes |  |  | Built | RiskDisclosure | flow |  |  | A worked demonstration of the whole arc, on illustrative data for a fictional partner rather than a real position. Public because the point is that a prospective investor can see every step - including the accreditation and disclosure they would meet later - before committing to any of it. | Step 3. Seven clauses in severity order, on paper. The gate opens on reaching the end by any route.
/how-capital-works | How Capital Works | capital | capital | public | yes | AS-04 | The Capital Explainer | Built | CapitalExplainer | gateway |  |  | The waterfall explainer is the single most important thing a prospective investor can read before committing, and putting it behind a sign-in would mean the disclosure only reaches people who have already decided.
/legal/risk-disclosure | Risk Disclosure | capital | capital | public | yes | AS-14 | The Risk Disclosure | Built | StandingDoc | documents |  |  | It gates commitment, and it is also the document a prospective investor most needs to read before deciding whether to start. Public to read; the ACKNOWLEDGEMENT still requires identity and is recorded against a version.
/member/entitlement | Entitlement | time | time | member | no | AS-25 | The Time Ledger | Scaffold | Surface (registry scaffold)
/member/entitlement/[year] | Entitlement Year | time | time | member | no | AS-25 | The Time Ledger | Scaffold | Surface (registry scaffold) |  |  | year
/flow/accreditation | Accreditation | member | member | public | yes |  |  | Built | Accreditation | flow |  |  | A worked demonstration of the whole arc, on illustrative data for a fictional partner rather than a real position. Public because the point is that a prospective investor can see every step - including the accreditation and disclosure they would meet later - before committing to any of it. | Step 2. PR-01, resumable - each field saves on blur to a draft record.
/flow/settled | Settled | member | member | public | yes |  |  | Built | Settled | flow |  |  | A worked demonstration of the whole arc, on illustrative data for a fictional partner rather than a real position. Public because the point is that a prospective investor can see every step - including the accreditation and disclosure they would meet later - before committing to any of it. | Step 5. The first screen where the Member Law has fired.
/member | Your Position | member | member | member | no | AS-05 | The Member Console | Scaffold | Surface (registry scaffold)
/member/calibration | Unit Calibration | member | member | member | no | AS-33 | The Member Surface | Built | Calibration | memberpages |  |  |  | MEM.05. Every control is real and none can be transmitted: the property is at pre-construction, so there is no management system to reach.
/member/calls | Capital Calls | member | member | member | no | AS-26 | The Capital Call | Scaffold | Surface (registry scaffold)
/member/calls/[ref] | Capital Call | member | member | member | no | AS-26 | The Capital Call | Scaffold | Surface (registry scaffold) |  |  | ref |  | Default consequences render in full above the payment control.
/member/codex | The Codex | member | member | member | no | AS-33 | The Member Surface | Built | Codex | memberpages |  |  |  | MEM.07. The manual for one property. The conduct-linked forced buyback the source specifies is marked as not drafted and not in force.
/member/distributions | Distributions | member | member | member | no | AS-05 | The Member Console | Scaffold | Surface (registry scaffold)
/member/distributions/[ref] | Distribution | member | member | member | no | AS-05 | The Member Console | Scaffold | Surface (registry scaffold) |  |  | ref
/member/documents | Documents | member | member | member | no | AS-05 | The Member Console | Scaffold | Surface (registry scaffold)
/member/documents/[id] | Document | member | member | member | no | AS-05 | The Member Console | Scaffold | Surface (registry scaffold) |  |  | id
/member/holdings | Holdings | member | space | public | yes | AS-10 | The Gallery Strip | Scaffold | Surface (registry scaffold)
/member/holdings/[property] | Holding | member | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property
/member/notifications | Notifications | member | member | member | no |  |  | Scaffold | Surface (registry scaffold) |  |  |  |  | The alert centre. A system ticker (SIGNAL_APERTURE) never lands here; only things asked of the member do.
/member/pass | Access Credentials | member | member | member | no | AS-33 | The Member Surface | Built | Pass | memberpages |  |  |  | MEM.08. Issuing spends your nights and puts the visitor's conduct on your record.
/member/position | Position | member | member | member | no | AS-05 | The Member Console | Scaffold | Surface (registry scaffold)
/member/profile | Passport | member | member | member | no | AS-33 | The Member Surface | Built | Passport | memberpages
/member/reports | Reports | member | member | member | no | AS-05 | The Member Console | Scaffold | Surface (registry scaffold)
/member/resolutions | Resolutions | member | member | member | no | AS-33 | The Member Surface | Built | Boardroom | memberpages
/member/resolutions/[ref] | Ballot | member | member | member | no | AS-27 | The Ballot | Scaffold | Surface (registry scaffold) |  |  | ref |  | Sealed at every vantage. The confirmation never echoes the choice.
/member/settings | Settings | member | member | member | no |  |  | Scaffold | Surface (registry scaffold)
/member/settings/notifications | Notification Settings | member | member | member | no |  |  | Scaffold | Surface (registry scaffold)
/member/settings/security | Security | member | member | member | no |  |  | Scaffold | Surface (registry scaffold)
/member/settings/tax | Tax Details | member | member | member | no |  |  | Scaffold | Surface (registry scaffold)
/member/signal | The Signal | member | member | member | no | AS-33 | The Member Surface | Built | SignalLog | memberpages |  |  |  | MEM.06. A written, asynchronous record with the operating partner. No presence indicator and no typing state — both promise an immediacy the queue does not have.
/passport | Your Passport | member | member | identified | no |  |  | Scaffold | Surface (registry scaffold) |  |  |  | The passport is how someone BECOMES a member. Requiring membership to reach it would close the only door into the system.
/passport/accreditation | Passport · accreditation | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/address | Passport · address | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/annual-review | Passport · annual review | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/decision | Passport · decision | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/discover | Passport · discover | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system. | Stage 1 of 16. Resumable — each field autosaves on blur to a draft record, which is what makes PR-01 genuinely resumable rather than a second mechanism.
/passport/documents | Passport · documents | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/eligibility | Passport · eligibility | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/identity | Passport · identity | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/issued | Passport · issued | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/profile | Passport · profile | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/review | Passport · review | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/risk-profile | Passport · risk profile | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/screening | Passport · screening | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/source-of-funds | Passport · source of funds | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/suitability | Passport · suitability | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/tax-residency | Passport · tax residency | member | capital | identified | no | AS-06 | The Commitment Flow | Scaffold | Surface (registry scaffold) |  |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/admin | Administration | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | organization.register
/admin/authority | Authority | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | authority.grant
/admin/authority/grants | Grants | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | authority.grant
/admin/authority/revocations | Revocations | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | authority.revoke
/admin/compliance | Compliance | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | compliance.record
/admin/compliance/accreditation | Accreditation Queue | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | accreditation.grant
/admin/compliance/conflicts | Conflict Register | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | conflict.disclose
/admin/compliance/events | Compliance Events | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | compliance.record
/admin/content | Content | admin | admin | office | no | AS-34 | The Admin Surface | Built | ContentAdmin | adminpages | content.publish |  |  | Every content class, its source, whether it binds and whether it is versioned.
/admin/failure | Constitutional Failure | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | constitutional_failure.declare |  |  | CF-01..CF-06. The gravest surface in the system and the least used. Declaring a failure requires a resolution reference, not a role — there is no login that can do this alone.
/admin/governance | Governance | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | resolution.table
/admin/governance/committees | Committees | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | committee.constitute
/admin/governance/policies | Policies | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | policy.approve
/admin/governance/resolutions | Resolutions | admin | member | member | no | AS-27 | The Ballot | Scaffold | Surface (registry scaffold) |  | resolution.table
/admin/governance/resolutions/[ref] | Resolution | admin | member | member | no | AS-27 | The Ballot | Scaffold | Surface (registry scaffold) |  | resolution.resolve | ref |  | Results only. Admin is NOT an exception to I-05 — it is the vantage most likely to assume it is.
/admin/ledger | Ledger | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | capital.deploy
/admin/media | Media | admin | admin | office | no | AS-34 | The Admin Surface | Built | MediaAdmin | adminpages | media.manage |  |  | Three kinds, required at registration with no default. A render registered as a photograph is a misrepresentation that needs no words.
/admin/reports | Reports | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | report.publish
/admin/research | Research | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | diligence.complete
/admin/telemetry | Telemetry | admin | admin | office | no |  |  | Scaffold | Surface (registry scaffold) |  | portfolio.manage
/admin/vehicles | Vehicles | admin | admin | office | no | AS-13 | The LLP Docket | Scaffold | Surface (registry scaffold) |  | vehicle.form
/admin/vehicles/[llpin] | Docket | admin | admin | office | no | AS-13 | The LLP Docket | Scaffold | Surface (registry scaffold) |  | vehicle.form | llpin
/admin/vehicles/[llpin]/audit | Docket Audit | admin | admin | office | no | AS-13 | The LLP Docket | Scaffold | Surface (registry scaffold) |  | compliance.record | llpin
/admin/vehicles/[llpin]/charges | Charges | admin | admin | office | no | AS-13 | The LLP Docket | Scaffold | Surface (registry scaffold) |  | vehicle.form | llpin
/admin/vehicles/[llpin]/filings | Statutory Calendar | admin | admin | office | no | AS-13 | The LLP Docket | Scaffold | Surface (registry scaffold) |  | compliance.record | llpin
/admin/vehicles/[llpin]/formation | Formation | admin | admin | office | no | AS-13 | The LLP Docket | Scaffold | Surface (registry scaffold) |  | vehicle.form | llpin
/admin/vehicles/[llpin]/partners | Register of Partners | admin | admin | office | no | AS-13 | The LLP Docket | Scaffold | Surface (registry scaffold) |  | vehicle.form | llpin
/admin/vehicles/[llpin]/resolutions | Resolutions | admin | admin | office | no | AS-13 | The LLP Docket | Scaffold | Surface (registry scaffold) |  | resolution.table | llpin
/admin/vehicles/new | Form a Vehicle | admin | admin | office | no | AS-34 | The Admin Surface | Built | VehicleFormation | adminpages | vehicle.form |  |  | Eight stages. Two irreversible, two gated on Board approval. §24a: the LLP is the default and any other legal form needs a resolution naming the specific property.

## Popups
Pop-ups, Modals & Dialogs
Two are built. The rest are proposed — read the Source column before treating any row as agreed. Every modal in this system closes on Escape AND on the backdrop, and its close control says Close, never Agree: a dialog whose only exit is 'I agree' collects consent from people trying to get rid of it.
ID | Where | Trigger | What it does | Ground | Status | Source | Notes
P-01 | /flow/accreditation | Read the Terms and Conditions button | Renders the full T&C document over the form. Gates the agreement checkbox — the box enables only once the document has been opened. | Paper | Built | Code | app/_assemblies/flow.tsx:577. Opens IN PLACE rather than linking away: a link loses the half-filled application. Does NOT require scrolling to the end — scroll position is not reading, and a keyboard user never fires a scroll handler.
P-02 | /gallery | Click a frame | Lightbox. Arrow keys step, Escape closes, close control always visible. | Void | Built | Code | app/_assemblies/gatewaypages.tsx:229. Close is never hover-revealed and never in a vanishing corner.
P-03 | All pages | First visit | Cookie / consent banner. | Paper | Not built | Proposed | /legal/cookies exists as a document with no banner in front of it. REQUIRED for DPDP and GDPR if you take EU traffic. Must default to declining non-essential.
P-04 | /flow/accreditation | Navigating away mid-form | Unsaved-changes guard. | Paper | Not built | Proposed | The form autosaves on blur, so this is lower risk than usual — but a half-finished PAN field is lost on a back button today.
P-05 | Any authenticated surface | Session nearing expiry | Session-expiry warning with an extend control. | Paper | Not built | Proposed | Blocked: no authentication exists. Build with Clerk, not before.
P-06 | /member/resolutions | Cast a vote | Vote confirmation. Contribution-weighted, irreversible, and states the weight being cast. | Paper | Not built | Proposed | A vote is irreversible under §24a. It needs the same deliberation treatment as the commitment piston, not an OK button.
P-07 | /admin/media | Upload | File picker with type, dimension and licence capture. | Paper | Not built | Proposed | The media admin surface is built; the upload path is not. Blocked on Vercel Blob.
P-08 | /admin/vehicles/new | Submit formation | Confirm-before-create for a new LLP. | Paper | Not built | Proposed | Creates a constitutional entity. Should require a resolution reference, not a click.
P-09 | Global | A destructive admin action | Confirm-destructive dialog. Types the object name to confirm. | Paper | Not built | Proposed | No destructive admin action is wired yet, so nothing is at risk today.
P-10 | /flow/commit | — | NONE, deliberately. | — | N/A | Code | The commitment is a 3-second sustained press (the piston), not a dialog. The duration IS the deliberation. A confirm dialog after a hold would be two confirmations, which trains people to dismiss both.

## Notifications
In-Product Notifications
Two routes exist to HOLD notifications; no notification is generated by anything. Every row below is Proposed unless marked otherwise. The trigger column names the event — a notification without a named event is a notification nobody can test.
ID | Event that fires it | Message | Audience | Urgency | Where it lands | Status | Source | Notes
N-00 | — | (the surfaces that hold them) | Member | — | /member/notifications, /member/settings/notifications | Scaffold | Code | Both routes exist and render the registry Surface. Nothing writes to them.
N-01 | Accreditation submitted | Application received. A decision follows within 15 working days. | Applicant | Normal | Email + in-product | Not built | Proposed | PR-01 states the window; nothing currently confirms receipt.
N-02 | Accreditation decided | Accreditation approved / declined, with the reason. | Applicant | High | Email + in-product | Not built | Proposed | A decline must state a reason and a route to appeal.
N-03 | Deposit received | ₹50,000 received. It holds your position; it does not make you a partner. | Investor | High | Email + in-product | Not built | Proposed | Must repeat the Member Law. The commonest misreading of a deposit is that it completes the purchase.
N-04 | Completion window opening | Balance and Vehicle Agreement due within 15 working days. | Investor | High | Email | Not built | Proposed | Needs a countdown, and a second at T-3 days.
N-05 | SETTLEMENT | You are a Member of <vehicle>. Entitlement and governance rights begin now. | Member | Critical | Email + in-product | Not built | Proposed | THE MEMBER LAW (I-08) fires here and only here. This is the single most important notification in the system and it is irreversible.
N-06 | Resolution opened | A resolution is open for your vote. Threshold: ordinary / special. Closes <date>. | Member | High | Email + in-product | Not built | Proposed | Must state the threshold and the voting weight, per §24a.
N-07 | Resolution closing | Your vote has not been cast. Voting closes in 48 hours. | Member | High | Email + in-product | Not built | Proposed | A tie is NOT approval, so an uncast vote has a real consequence and the reminder must say so.
N-08 | Resolution decided | Outcome, the count, and the threshold it met. | Member | Normal | Email + in-product | Not built | Proposed | ADR-0008: secret ballot, transparent outcome. Publish the tally, never who voted how.
N-09 | Distribution declared | <amount> declared for the period ending <date>. | Member | Normal | Email + in-product | Not built | Proposed | Must carry a confidence class like every other figure.
N-10 | Distribution paid | <amount> paid to the account ending <n>. | Member | Normal | Email + in-product | Not built | Proposed
N-11 | Distribution BLOCKED | No distribution this period. Stage six does not run if the reserve would fall below its floor. | Member | High | Email + in-product | Not built | Proposed | Silence here reads as an error. A profitable period with no distribution is normal and must be explained when it happens, not in a FAQ.
N-12 | Entitlement opens | Your <n> nights for <year> are now drawable. | Member | Normal | In-product | Not built | Proposed | Not before handover — nothing is drawable against an unbuilt asset.
N-13 | Entitlement expiring | <n> nights lapse on <date>. | Member | Normal | Email + in-product | Not built | Proposed | Needs a stated lapse policy first — see Decisions D-07.
N-14 | Document version changed | <document> is now v<n>. What changed: <summary>. | Member | High | Email | Not built | Proposed | A binding document changing under someone silently is the failure mode. Must link the diff.
N-15 | Covenant proximity | DSCR approaching the covenant threshold. | Office | Critical | In-product | Not built | Proposed | Office vantage only. Never shown at member vantage without Board sign-off on the wording.
N-16 | Valuation published | <property> revalued to <amount> by <source>. | Member | Normal | In-product | Not built | Proposed | Must name the source and its confidence class; a management estimate is not an appraisal.
N-17 | Lead captured | A signal / dossier request arrived. | Office | Low | Email | Live | Code | The only notification that actually fires today. app/api/signal, app/api/dossier → lib/leads.ts.

## Emails
Transactional Email
Two endpoints are live via Resend; both return 503 without RESEND_API_KEY and the page says so rather than showing a false success. Everything else is proposed. No template system, no unsubscribe handling and no verified sending domain exists yet.
ID | Trigger | To | Subject / purpose | Type | Template | Status | Source | Notes
E-01 | /signal form submit | SIGNAL_LEAD_EMAIL | New Signal subscriber | Internal | Plain text | Live | Code | lib/leads.ts. Returns 503 when unconfigured; the form renders an honest failure with a mailto fallback.
E-02 | /communique/request submit | DOSSIER_LEAD_EMAIL | New dossier request | Internal | Plain text | Live | Code | Same path. 400 on invalid input, 503 on unconfigured.
E-03 | Signal form submit | The subscriber | Confirm the subscription (double opt-in) | Outbound | — | Not built | Proposed | REQUIRED. Today you capture an address and send that person nothing — no confirmation and no way to unsubscribe. This is a compliance gap, not a nicety.
E-04 | Dossier request | The requester | The dossier itself | Outbound | — | Not built | Proposed | The form promises an intelligence pack. Nothing sends one. See Assets A-20.
E-05 | Sign-up | New account | Verify your email address | Outbound | — | Not built | Proposed | Blocked on Clerk, which handles this natively.
E-06 | Accreditation submitted | Applicant | Application received · 15 working days | Outbound | — | Not built | Proposed | Pairs with N-01.
E-07 | Accreditation decided | Applicant | Decision, with reason | Outbound | — | Not built | Proposed | Pairs with N-02.
E-08 | Deposit received | Investor | ₹50,000 received · what it does and does not do | Outbound | — | Not built | Proposed | Must state that a deposit makes nobody a partner.
E-09 | Deposit received | Investor | Payment receipt (GST-compliant) | Outbound | — | Not built | Proposed | Tax-document requirements unconfirmed — see Decisions D-05.
E-10 | Settlement | Member | You are a Member of <vehicle> | Outbound | — | Not built | Proposed | THE MEMBER LAW. Should carry the Vehicle Agreement and the register entry as attachments.
E-11 | Resolution opened | Members | A resolution is open · closes <date> | Outbound | — | Not built | Proposed
E-12 | Resolution closing | Non-voters | Voting closes in 48 hours | Outbound | — | Not built | Proposed
E-13 | Resolution decided | Members | Outcome and tally | Outbound | — | Not built | Proposed | Tally yes; individual votes never.
E-14 | Distribution paid | Member | Distribution statement | Outbound | — | Not built | Proposed | Needs a PDF generator — none exists.
E-15 | Quarterly | Members | Vehicle report | Outbound | — | Not built | Proposed | Cadence and content not agreed — Decisions D-08.
E-16 | Document version change | Members | <document> updated to v<n> | Outbound | — | Not built | Proposed | Legally significant. Must link the diff, not just announce it.
E-17 | Weekly | Signal subscribers | The Signal | Marketing | — | Not built | Proposed | Needs unsubscribe, preference centre and a verified domain before a single send.
E-18 | Password reset | Account | Reset your password | Outbound | — | Not built | Proposed | Blocked on Clerk.

## Gaps
Current Gaps
What is missing, why it matters, and what it blocks. Severity is my assessment. 'Blocks launch' means I would not put the URL in front of an investor until it is closed.
ID | Area | The gap | What it blocks | Severity | Effort | Status | Source | Notes
G-01 | Legal | ~9,000 words of Terms and Risk Disclosure have never been reviewed by a lawyer. | Any real investor traffic | Blocks launch | External | Open | Code | content/legal.ts + slowspace.ts. Drafted to be accurate; not drafted to be relied on. This is the single largest exposure on this sheet and it is not a code problem.
G-02 | Legal | Repository is PUBLIC, so the unreviewed copy and the LLP identifiers are world-readable. | — | Blocks launch | Minutes | Open | Code | One command flips it. Raised twice; not yet actioned.
G-03 | Entity | SlowSpace Coastal LLP, LLPIN AAC-4471 and the Udupi registered office are modelled from a dossier, not verified against the MCA register. | Publishing the offering | Blocks launch | External | Open | Code | If the entity is not incorporated with that identifier, the platform is asserting that it is.
G-04 | Auth | No authentication. lib/access.ts fails closed, so 63 member/office routes correctly deny everyone. | Every member and office surface | High | Large | Open | Code | Deliberate and correct for an unfinished system. Clerk is chosen but not integrated.
G-05 | Data | No database. Every page reads static TypeScript. | Persistence of anything | High | Large | Open | Code | Drizzle schema and 27 tables are generated and checked; nothing connects to Neon.
G-06 | Payments | No payment processor. The ₹50,000 deposit cannot be taken. | The commitment flow | High | Large | Open | Code | Razorpay chosen. The piston records a state change in memory and nothing else.
G-07 | Product | 82 of 135 routes render the registry Surface scaffold, not the product. | Depth beyond the built paths | High | Large | Open | Code | See the IA sheet. 12 of these are PUBLIC and indexable — the highest-priority subset.
G-08 | Media | No photography exists. The gallery ships five labelled drawings. | Every visual surface | High | External | Open | Code | content/gateway.ts states this plainly rather than shipping renders as photographs. See the Assets sheet.
G-09 | Ops | No error tracking. | Knowing when production breaks | High | Small | Open | Doc | Sentry identified as the sixth account; not opened.
G-10 | Ops | No rate limiting on /api/signal or /api/dossier. | Publicising the URL | High | Small | Open | Code | Both are public, unauthenticated and send email. Trivially abusable once the domain is known.
G-11 | Compliance | No cookie/consent banner, no unsubscribe, no double opt-in. | EU traffic; any marketing send | High | Medium | Open | Code | /legal/cookies documents a policy nothing enforces.
G-12 | Ops | No CI. npm run verify runs only via a local pre-commit hook, which --no-verify walks past. | Confidence in main | Medium | Small | Open | Code | GitHub Actions workflow not yet added; the token scope for it exists.
G-13 | Product | Notifications: two routes hold them, nothing generates one. | Every member communication | Medium | Medium | Open | Code | See the Notifications sheet.
G-14 | Product | No PDF generation. | Statements, receipts, the dossier | Medium | Medium | Open | Proposed | Referenced by four proposed emails.
G-15 | Design | Risk categories: 8 in the design system, 10 in the registry. Six render neutral grey. | Correct risk colour | Medium | Small | Open | Doc | WAVE-5-OPEN-QUESTIONS A2. riskColour() falls back to steel and a test pins that.
G-16 | Design | Brand voice conflict: L1-02 says 'Warm', Addendum A says 'never persuades'. | Consistent copy | Low | Small | Open | Doc | WAVE-5 A1. Resolved in practice toward plain and non-blaming; not written down.
G-17 | Content | /collective/press and /collective/gallery ship empty on purpose. | Credibility surfaces | Low | External | Open | Code | The wireframe's six press clippings were quotes attributed to publications that have not published them. Empty and honest beats populated and false.
G-18 | Ops | Vercel region pinned to bom1 for DPDP residency; plan support unverified. | First deploy | Low | Minutes | Open | Code | vercel.json. Will fail the deploy if the plan disallows region pinning.

## Decisions
Decisions Awaiting You
Each is a decision I could not make for you because it is commercial, fiduciary, legal or a matter of taste. Where I had a defensible default I applied it and said so in My Recommendation — none of those is agreed. YELLOW CELLS ARE YOURS TO FILL.
ID | Area | The decision | My recommendation | Source | Your decision | Owner | Status | Due
D-01 | Legal | Engage a lawyer to review the Terms and Risk Disclosure before any real traffic. Who, and when? | Do this before the domain is public. Nothing else on this sheet costs more to get wrong. | Code |  |  | Open
D-02 | Legal | Repository visibility: public or private? | Private until D-01 closes. Search engines cannot un-crawl. | Code |  |  | Open
D-03 | Entity | Confirm SlowSpace Coastal LLP is incorporated, and the real LLPIN and registered office. | Replace with placeholders until confirmed, or confirm and keep. | Code |  |  | Open
D-04 | Commercial | Minimum unit is 5% and the ceiling 50%. Confirm both. | Keep. 5% admits a wider register; 50% is where a partner would carry every ordinary resolution alone under §24a. | Code |  |  | Open
D-05 | Finance | Is the ₹50,000 deposit taxable on receipt, and what document must issue? | Needs your accountant. It changes E-09 and the receipt wording. | Proposed |  |  | Open
D-06 | Commercial | Confirm the entitlement pool of 180–210 nights a year for the whole property. | Keep. Derived so that no partition can exceed what the property can deliver. | Code |  |  | Open
D-07 | Commercial | Do unused nights lapse, roll over, or convert? | Needs a policy before N-13 can be written. Lapse is simplest and the least generous; say which it is. | Proposed |  |  | Open
D-08 | Comms | Reporting cadence to members — quarterly, half-yearly? | Quarterly, aligned to the distribution period. | Proposed |  |  | Open
D-09 | Design | Risk categories: extend the design system to 10, or map the registry's 10 onto 8? | Map first (no amendment needed), then extend. | Doc |  |  | Open
D-10 | Brand | Brand voice: does L1-02 'Warm' or Addendum A 'never persuades' govern interface copy? | Addendum A governs interface copy; L1-02 governs member-facing narrative. Write it down. | Doc |  |  | Open
D-11 | Ops | Confirm the production domain. | getawaycollective.in is assumed throughout .env.example. Every share card and sitemap URL depends on it. | Code |  |  | Open
D-12 | Ops | Confirm the Vercel plan supports region pinning to bom1. | Needed for the DPDP residency claim. If not, either upgrade or drop the claim — do not keep the claim without the pinning. | Code |  |  | Open
D-13 | Ops | Open a Sentry account (the sixth). | Yes, before launch. Silent production failures are the worst kind. | Doc |  |  | Open
D-14 | Media | Commission photography, or ship labelled drawings? | Ship drawings, labelled as drawings, until a property is photographable. Commission for Padubidri at handover. | Code |  |  | Open
D-15 | Product | Which of the 12 public scaffolds get built first? | See the IA sheet filtered to public + scaffold. They are indexable, so they are what a stranger finds. | Code |  |  | Open
D-16 | Comms | Verify a sending domain in Resend. | Required before any outbound email. The sandbox sender only delivers to your own address. | Code |  |  | Open
D-17 | Legal | Do you take EU traffic? It decides whether GDPR applies on top of DPDP. | Assume yes unless you geo-block. It changes P-03 and E-03. | Proposed |  |  | Open
D-18 | Domain | Ratify the §33 amendment queue: 10 candidate objects the vehicle domain model registers (see the Domain sheet). | Ratify OwnershipCalendar + AllocationRight first — Time is the only domain with zero ratified objects. FixedAsset and DebtFacility next; both are needed before the first fit-out invoice and the first covenant test. | Code |  |  | Open
D-19 | Domain | Confirm the audit-threshold policy: the statutory mirror assumes EVERY GC vehicle crosses ₹25 lakh contribution at formation, so all are audited and ITR-5 falls on 31 October. | True of SlowSpace (₹4 Cr equity). Confirm it holds as standing policy so the mirror never needs a per-vehicle exception. | Code |  |  | Open
Note on F5: Fill these four columns. Everything to the left is derived and will be overwritten if this workbook is regenerated.

## Assets
Pending Assets
Nothing here exists. Dimensions are what the code actually consumes; where a surface currently renders a generated placeholder, the placeholder is named so you can see what it is standing in for. YELLOW CELLS ARE YOURS.
ID | Category | Asset | Type | Dimensions | Qty | Used by | Currently renders | Status | Owner | Due
A-01 | Brand | Wordmark | SVG | Vector, 1-colour | 1 | Header, footer, favicon | Text 'GC.SYSTEM' | Not supplied
A-02 | Brand | Monogram / favicon | SVG | Square, legible at 16px | 1 | app/icon.tsx | Generated GC monogram from tokens | Not supplied
A-03 | Brand | Brand guidelines PDF | PDF | — | 1 | Partner and press packs | — | Not supplied
A-04 | Property | SlowSpace Coastal · hero | Photo/render | 3200×1800 (16:9), ≥2× retina | 1 | /flow, /collection/[property] | Generated gradient plate, hue 198 | Not supplied
A-05 | Property | SlowSpace Coastal · gallery set | Photo/render | 2400×3000 (4:5) | 8–12 | /gallery, /collection/[property]/gallery | 2 labelled drawings (F-01, F-02) | Not supplied
A-06 | Property | SlowSpace Coastal · site plan | Drawing | Vector or 3000px wide | 1 | /collection/[property]/location | F-02 placeholder | Not supplied
A-07 | Property | SlowSpace Coastal · section drawings | Drawing | Vector | 3–4 | Space surfaces | F-01 placeholder | Not supplied
A-08 | Property | Kyoto House · gallery set | Photo | 2400×3000 (4:5) | 6–10 | /collection/kyoto-house | 1 labelled drawing (F-03) | Not supplied
A-09 | Property | Swiss Vault · gallery set | Photo | 2400×3000 (4:5) | 6–10 | /collection/swiss-vault | 1 labelled drawing (F-04) | Not supplied
A-10 | Property | Oslo Base · gallery set | Photo | 2400×3000 (4:5) | 6–10 | /collection/oslo-base | 1 labelled drawing (F-05) | Not supplied
A-11 | Property | Aerial / context | Photo | 3200×1800 | 1 per property | Location surfaces | — | Not supplied
A-12 | Social | Default share card | PNG | 1200×630 | 1 | app/opengraph-image.tsx | Generated type-only card from tokens | Not supplied
A-13 | Social | Per-property share cards | PNG | 1200×630 | 1 per property | Property routes | Falls back to A-12 | Not supplied
A-14 | Editorial | Journal entry headers | Photo/illustration | 2400×1350 (16:9) | 1 per entry | /journal/[slug] | Gradient plate | Not supplied
A-15 | Editorial | Journal author portraits | Photo | 800×800 | 1 per author | /journal/[slug] | — | Not supplied
A-16 | People | Team portraits | Photo | 1200×1500 (4:5) | 1 per person | /roles/[code] | — | Not supplied
A-17 | Partners | Partner firm logos | SVG | Vector, 1-colour | 1 per firm | /collective/partners | Names withheld until engagements are recorded | Not supplied
A-18 | Diagram | Vehicle / entity structure | SVG | Vector | 1 | /structure, /how-it-works | Text-and-rule diagram | Not supplied
A-19 | Diagram | Waterfall diagram | SVG | Vector | 1 | /how-capital-works | Built in CSS from live figures — arguably better than an asset | Not supplied
A-20 | Document | The Dossier / investment brief | PDF | A4 | 1 | /communique/request | NOTHING. The form promises it and no file exists. | Not supplied
A-21 | Document | Vehicle Agreement template | PDF/DOCX | A4 | 1 per vehicle | Accreditation, settlement | — | Not supplied
A-22 | Press | Press kit | ZIP | — | 1 | /collective/press | Ships empty and says so | Not supplied
A-23 | Video | Property film | MP4 | 1920×1080, ≤60s | 1 per property | Hero surfaces | — | Not supplied
A-24 | Legal | Lawyer-reviewed Terms and Risk Disclosure | Text | — | 1 | content/legal.ts | Unreviewed draft, ~9,000 words | Not supplied

## Domain
The Vehicle Domain Model
EXTRACTED from constants/vehicle-domain.ts (commit b0ade3f), not typed. The LLP sits at the apex; Space, Time and Capital are its constituents; Governance is the constitutional layer that governs the other three — not a fourth business function. Every constituent states what backs it: a ratified object, a UFR field, a derivation, executable code, a REGISTERED gap awaiting a §33 amendment, or OUT OF SCOPE with the reason.
Domain | Section | Constituent | Backing | Backed by | Gap / exclusion detail | Note
Space | What does the LLP own?
| SP.1 · Property | Property Code | object | Property |  | The asset code (PDB-01) is carried on the record today; a dedicated UFR entry is the E-06 gap to close when the field is next touched.
| SP.1 · Property | Property Name | field | UFR-0060 on Property
| SP.1 · Property | Property Type | object | Property |  | Carried on the Property record; the closed type set is an enum question, not a new object.
| SP.1 · Property | Investment Thesis | object | Investment Thesis |  | An attribute of the asset, constitutionally: the thesis names why THIS property. It moved from Intelligence to Space for that reason.
| SP.1 · Property | Asset Status | field | UFR-0066 on Property |  | The lifecycle field. Pre-construction → construction → stabilised → disposition.
| SP.1 · Property | Documents Folder | registered | PropertyDocument | One object per instrument with kind, custody and hash — a folder is not a record.
| SP.2 · Fixed Assets | Furniture & Fixtures | registered | FixedAsset | Asset register entries with cost, life, and depreciation basis. Required before the first fit-out invoice lands.
| SP.2 · Fixed Assets | Plant & Machinery | registered | FixedAsset | Same object, classed plant_machinery.
| SP.2 · Fixed Assets | Renewable Systems | registered | FixedAsset | Same object, classed renewable.
| SP.2 · Fixed Assets | Capital Improvements | registered | FixedAsset | Same object, classed improvement — funded from the Sinking Fund, which is why the class must be distinguishable.
| SP.3 · Asset Protection | Insurance | registered | InsurancePolicy | Policy, insurer, sum insured, expiry. The governance calendar needs the expiry date to fire a compliance event.
| SP.3 · Asset Protection | Valuation | object | Valuation |  | Already ratified. Carries its source and confidence class — a management estimate is not an appraisal.
| SP.4 · Property Documents | Drawings | registered | PropertyDocument | kind: drawing
| SP.4 · Property Documents | Approvals | registered | PropertyDocument | kind: approval. CRZ clearance lives here — the compliance mirror in Governance references it.
| SP.4 · Property Documents | Manuals | registered | PropertyDocument | kind: manual
| SP.4 · Property Documents | Warranties | registered | PropertyDocument | kind: warranty. Expiry-bearing, like insurance — feeds the governance calendar.
| SP.4 · Property Documents | Asset Registers | registered | FixedAsset | The register IS the set of FixedAsset records; a separate register document would be a copy that drifts.
Time | How much time does each LLP Partner legally control?
| TM.1 · Ownership Calendar | Calendar Year | registered | OwnershipCalendar | One record per vehicle per year. The vehicle-level pool the allocations divide.
| TM.1 · Ownership Calendar | Allocation Year | registered | OwnershipCalendar | The year an allocation belongs to — distinct from the calendar year it is used in only once rollover policy exists, which is Decision D-07.
| TM.1 · Ownership Calendar | Available Days | derived | NIGHT_POOL stated per vehicle per year; each position takes floor(pool × stake) |  | The pool is stated for the whole vehicle and each position takes its floor, so the sum of every partner's entitlement can never exceed what the property delivers. Multiplying a per-unit figure would invent nights.
| TM.2 · Allocation Rights | Ownership Percentage | field | UFR-0242 on Ownership Position |  | units_held over total_units_issued. The stake is the input; time is one of its outputs.
| TM.2 · Allocation Rights | Annual Day Allocation | derived | floor(available_days × ownership_percentage) |  | STATIC. It does not vary with usage, season or behaviour — a right attached to ownership, not a reward attached to conduct.
| TM.2 · Allocation Rights | Reserved Days | registered | AllocationRight | Days the vehicle withholds from the pool before division — maintenance closures, statutory closures.
| TM.2 · Allocation Rights | Blackout Rules | registered | AllocationRight | Vehicle-level rules constraining when allocation may be drawn. Rules, never individual draws.
| TM.3 · Usage Rights | Usage Rights | outOfScope |  | Directed out of scope, 1 Aug 2026. Usage is operation, and operation belongs to the Operating Company. The vehicle records who CONTROLS time, never who USED it.
| TM.4 · Calendar Rights | Calendar Rights | outOfScope |  | Directed out of scope, 1 Aug 2026. Same boundary as Usage Rights.
| TM.5 · Time Ledger | Time Ledger | outOfScope |  | Directed out of scope, 1 Aug 2026. A ledger of draws is an operating record. If it is ever pulled inside the vehicle, it enters as a §33 amendment — not as a quiet table.
Capital | What is the financial position of the LLP?
| CP.1 · Investors | Partner Register | object | Investor
| CP.1 · Investors | Ownership Register | object | Ownership Position |  | The same record Time reads its stake from. One register, two domains reading it — never two registers.
| CP.1 · Investors | Capital Accounts | registered | CapitalAccount | Per-partner: contributed, share of profit, drawings, closing balance. The LLP Act requires it and Schedule-form accounts assume it.
| CP.2 · Capital Formation | Investment Offering | object | Investment Offering
| CP.2 · Capital Formation | Commitments | object | Commitment
| CP.2 · Capital Formation | Contributions | object | Investment |  | A settled contribution. The Member Law fires here and nowhere else.
| CP.2 · Capital Formation | Capital Calls | object | Capital Call
| CP.3 · Finance | Debt | registered | DebtFacility | Lender, principal, rate, moratorium, covenants. The ₹5.5 Cr facility currently lives as prose in slowspace.ts — a covenant nobody can query is a covenant nobody monitors.
| CP.3 · Finance | Interest | registered | DebtFacility | Schedule rows on the facility.
| CP.3 · Finance | Repayments | registered | DebtFacility | Schedule rows on the facility.
| CP.3 · Finance | Banking | registered | BankAccount | Account, bank, signatories. Signing authority itself is Governance — the account is Capital, the authority over it is law.
| CP.4 · Revenue | Revenue | registered | LedgerEntry | Recognised revenue, by period and class.
| CP.4 · Revenue | Operating Income | registered | LedgerEntry | class: operating
| CP.4 · Revenue | Brand Income | registered | LedgerEntry | class: brand
| CP.4 · Revenue | Other Income | registered | LedgerEntry | class: other
| CP.5 · Expenses | Operating Costs | registered | LedgerEntry | class: operating_cost
| CP.5 · Expenses | Asset Management | registered | LedgerEntry | class: asset_management
| CP.5 · Expenses | Administration | registered | LedgerEntry | class: administration
| CP.5 · Expenses | Insurance | registered | LedgerEntry | class: insurance — the premium is an expense here; the policy is Space (SP.3).
| CP.5 · Expenses | Professional Fees | registered | LedgerEntry | class: professional_fees
| CP.6 · Reserves | Sinking Fund | code | lib/domain.ts — waterfall stage 4, floor rule F-06 |  | The reserve exists as executable law: 2.5% of revenue in, distribution blocked if paying would breach the floor. A Reserve record joins when persistence exists.
| CP.7 · Valuation | NAV | derived | asset valuations (Space) − debt outstanding + reserves + net working capital |  | Derived, never typed. The prototype carried four different valuations of one house because each screen held its own copy.
| CP.8 · Distribution | Waterfall | code | lib/domain.ts — six stages, closes to 100%, F-05
| CP.8 · Distribution | Debt Service | derived | investor share − partner distribution; stage 5, the senior claim
| CP.8 · Distribution | Partner Distributions | object | Distribution
| CP.8 · Distribution | Retained Earnings | derived | what stage 6 withholds when blocked — retained, never evaporated
| CP.9 · Reporting | Balance Sheet | object | Performance Report |  | Statement kinds on the report object; the statutory filing of them is Governance (Form 8).
| CP.9 · Reporting | Profit & Loss | object | Performance Report
| CP.9 · Reporting | Cash Flow | object | Performance Report
| CP.9 · Reporting | Capital Accounts | registered | CapitalAccount | Reported per partner, per period — same object as CP.1.
| CP.9 · Reporting | Forecasts | object | Forecast |  | Forward-looking, so every figure carries its confidence class.
Governance ⚖ | Under what law does the LLP act, and can it prove compliance?
| GV.1 · LLP Governance | LLP Agreement | object | Agreement |  | The constitutional instrument. Filed as Form 3 within 30 days of incorporation — the statutory mirror row references this record.
| GV.1 · LLP Governance | Partner & Designated Partner Register | object | Investor |  | The register read here is the same Investor set Capital holds — annotated with designated-partner status, never duplicated.
| GV.1 · LLP Governance | Authority Matrix | code | lib/authority.ts — rights, roles, separationViolations() |  | Executable, and checked: no role may hold a dangerous triad. A matrix kept as a document is a matrix nobody enforces.
| GV.1 · LLP Governance | Board / Partner Meeting Records | object | Committee
| GV.1 · LLP Governance | Resolution Register | object | Resolution
| GV.1 · LLP Governance | Voting Register | code | constants/voting.ts — thresholds; ADR-0008 secret ballot, transparent outcome |  | Contribution-weighted per §24a. Ordinary carries above 50% — a tie is not approval. Special at 76%. Tallies are published; who voted how never is.
| GV.1 · LLP Governance | Constitutional Amendments | object | Policy |  | Including §33 amendments — which is how every `registered` candidate in this file becomes real.
| GV.1 · LLP Governance | All Agreements | object | Agreement |  | Operator agreement, brand licence, facility agreement — one object, kinds distinguished. Every contract the vehicle signs lands here or does not bind it.
| GV.2 · Corporate Administration | Incorporation Documents | registered | StatutoryRecord | kind: incorporation — certificate, LLPIN, Form 2.
| GV.2 · Corporate Administration | PAN | registered | StatutoryRecord | kind: pan
| GV.2 · Corporate Administration | TAN | registered | StatutoryRecord | kind: tan — required the day the first salary or contractor payment is made, for TDS.
| GV.2 · Corporate Administration | Registered Office | registered | StatutoryRecord | kind: registered_office. No UFR field carries it today — LLP.office in slowspace.ts is prose. A change of registered office is Form 15; the mirror row exists below.
| GV.2 · Corporate Administration | Statutory Registers | registered | StatutoryRecord | kind: register
| GV.2 · Corporate Administration | Digital Signatures | registered | StatutoryRecord | kind: dsc — every designated partner needs one before any MCA filing can be made.
| GV.2 · Corporate Administration | Banking Authorities | registered | StatutoryRecord | kind: banking_authority — WHO may operate the account. The account itself is Capital (CP.3).
| GV.2 · Corporate Administration | Authorised Signatories | registered | StatutoryRecord | kind: signatory
| GV.2 · Corporate Administration | Enterprise Policies | object | Policy
| GV.2 · Corporate Administration | Governance Calendar | derived | union of every statutory due date below + every expiry-bearing record (insurance, warranties, DSC) |  | Derived from the obligations, never kept by hand. A hand-kept calendar is the one document guaranteed to be wrong the year it matters.
THE STATUTORY MIRROR | Every obligation of an Indian LLP, mapped onto the ComplianceEvent object — the governance calendar is derived from these rows, never kept by hand.
Ref | Instrument | Authority |  | What | Due | Applies when
ST-01 | Form 3 | MCA |  | File the LLP Agreement and any change to it. | Within 30 days of incorporation or of the change | always
ST-02 | Form 11 | MCA |  | Annual Return — partners, contributions, changes in the year. | Within 60 days of financial year end (by 30 May) | always
ST-03 | Form 8 | MCA |  | Statement of Account & Solvency — the accounts CP.9 produces, filed. | By 30 October each year | always
ST-04 | Statutory audit | MCA |  | Audit of the accounts. | Before Form 8 | turnover > ₹40 lakh OR contribution > ₹25 lakh — every GC vehicle crosses the second test at formation
ST-05 | ITR-5 | Income Tax |  | Income tax return of the LLP. | 31 July, or 31 October when audited — GC vehicles are audited, so 31 October | always
ST-06 | TDS returns (24Q/26Q) | Income Tax |  | Quarterly deduction returns against the TAN. | Quarterly | any payment attracting TDS — contractor, professional fees, interest
ST-07 | GST returns | GST |  | Registration and periodic returns. | Monthly/quarterly per registration | taxable supplies exceed the threshold — expected once operations begin
ST-08 | Form 4 | MCA |  | Change of partner or designated partner. | Within 30 days of the change | on every admission, resignation or transfer — every settlement that admits a partner fires this
ST-09 | Form 15 | MCA |  | Change of registered office. | Within 30 days | on relocation
ST-10 | DIR-3 KYC | MCA |  | Annual KYC of every designated partner's DPIN. | By 30 September each year | always
ST-11 | CRZ clearance conditions | State |  | Conditions attached to the Coastal Regulation Zone approval — the approval itself is a Property Document (SP.4). | As conditioned | coastal properties — SlowSpace Coastal is one
§33 AMENDMENT QUEUE | Candidate objects the model needs and the ratified 27 do not contain. Ratifying one moves its constituents from `registered` to `object` without restructuring anything. This is Decision D-18.
| AllocationRight | needed by 2 constituent(s)
| BankAccount | needed by 1 constituent(s)
| CapitalAccount | needed by 2 constituent(s)
| DebtFacility | needed by 3 constituent(s)
| FixedAsset | needed by 5 constituent(s)
| InsurancePolicy | needed by 1 constituent(s)
| LedgerEntry | needed by 9 constituent(s)
| OwnershipCalendar | needed by 2 constituent(s)
| PropertyDocument | needed by 5 constituent(s)
| StatutoryRecord | needed by 8 constituent(s)