## README
Getaway Collective · Build State
Generated 1 Aug 2026 from the repository at C:\gc-app, commit d58044a
WHAT THIS IS | Every addressable surface, pop-up, notification and email in the platform, with what is built, what is not, and what is waiting on you. The Domain sheet carries the constitutional model: the LLP at the apex, Space / Time / Capital beneath it, Governance as the operating law.
HOW IT WAS MADE | The IA sheet is EXTRACTED, not typed. constants/routes.ts is imported directly and each row's status is read from the generated page file on disk — so this workbook cannot disagree with the application about what exists.
THE SOURCE COLUMN | The single most important column on every sheet after IA. It separates fact from opinion:
Code | Extracted from the repository. Verifiable — the file and line are named.
Doc | Stated in a repository document (WAVE-5-OPEN-QUESTIONS.md, WAVE-6-CHANGELOG.md).
Proposed | MY RECOMMENDATION. Not in the repo, not agreed by you, and not built. Nothing marked Proposed has been decided.
STATUS VALUES
Built | Renders the real interface.
Scaffold | Renders the registry Surface: the assembly's declared sections and rules, not the product. It is deliberately obvious that it is a scaffold — a scaffold that looks finished gets signed off.
Not built | Nothing exists.
Framework | Handled by a Next.js convention file rather than a page (/404 → not-found.tsx).
CELLS YOU EDIT | Yellow. They are on the Decisions and Assets sheets — the Decision / Owner / Due / Status columns. Everything else is derived and will be overwritten when this is regenerated.
WHAT IS NOT HERE | Database, authentication and payments. None of the three exists — every page reads static TypeScript. See the Gaps sheet.

## Summary
Build State · Summary
Every figure is a COUNTIF against the IA sheet. Re-derive by regenerating IA; nothing here is typed.
BY STATUS |  |  | Scaffold = renders the registry Surface, which shows the assembly's declared sections and rules. It is the product's outline, not the product.
| Count | % of total
Built | 133 | 98.52%
Scaffold | 0 | 0%
Framework | 2 | 1.481%
Not built | 0 | 0%
Total | 135 | 100%
BY ACCESS |  |  | Access is DERIVED from the assembly's vantage, not declared per route. Twelve routes override it, and route-lint refuses an override without a stated reason.
| Count | % of total
public | 51 | 37.78%
identified | 18 | 13.33%
accredited | 3 | 2.222%
member | 26 | 19.26%
office | 37 | 27.41%
Total | 135 | 100%
BY GROUP
| Count | % of total
gateway | 37 | 27.41%
space | 7 | 5.185%
capital | 18 | 13.33%
time | 2 | 1.481%
member | 42 | 31.11%
admin | 29 | 21.48%
Total | 135 | 100%
CROSS-CUT
Public AND built | 49 |  | What a stranger can actually see today.
Public AND scaffold | 0 |  | Public URLs that render an outline. These are indexable — the highest-priority build queue.
Indexable | 51 |  | Must equal the public count: route-lint refuses an indexable route that is not public.
Office routes with rights | 37 |  | Office routes naming a required right from lib/authority.ts.
Dynamic routes | 29 |  | Carry at least one [param] segment.
Access overrides | 27 |  | Each states its reason on the IA sheet.
OTHER SHEETS
Pop-ups built | 2
Pop-ups deliberately none | 1
Pop-ups to build | 7
Notifications firing today | 1
Notifications to build | 16
Emails live | 2
Emails to build | 16
Open gaps | 27
Decisions awaiting you | 29
Assets outstanding | 24
Domain constituents | 76
— backed by ratified object/field | 25
— derived or executable law | 10
— registered gaps (§33 queue) | 38
— out of scope by direction | 3

## IA
Information Architecture
Every URL in the system. Extracted from constants/routes.ts; Status read from the generated page file on disk. Nothing else in the platform holds a URL — a path not on this sheet does not exist.
Path | Name | Group | Vantage | Access | Indexable | Assembly | Assembly Name | Status | Rendered By | Module | Rights | Params | Access Override — why | Notes
/ | Home | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Root | publicpages |  |  |  | Hero region, then routes into the collection. No figure above the fold.
/403 | Not Permitted | gateway | gateway | public | yes | AS-16 | Signal Lost | Built | Composed | compose |  |  |  | Says the viewer may not see it. Never says whether it EXISTS — that distinction leaks the shape of the system to anyone probing it.
/404 | Not Found | gateway | gateway | public | yes | AS-16 | Signal Lost | Framework | [5 empty] | No stack trace, no exception name, no auto-redirect. [extract] No page.tsx: Next.js serves this from app/not-found.tsx / app/error.tsx by convention.
/500 | System Error | gateway | gateway | public | yes | AS-16 | Signal Lost | Framework | [5 empty] | [extract] No page.tsx: Next.js serves this from app/not-found.tsx / app/error.tsx by convention.
/answers | Answers | gateway | gateway | public | yes | AS-17 | The Knowledge Base | Built | Answers | gatewaypages
/auth/sign-in | Identify | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Identify | publicpages |  |  |  | No password is ever handled by the design system. Delegated.
/auth/sign-out | Sign Out | gateway | gateway | public | yes |  |  | Built | Composed | compose
/auth/verify | Verify | gateway | gateway | public | yes |  |  | Built | Composed | compose |  |  |  | The token arrives as a QUERY parameter, not a path segment, and it is not declared as a param for that reason. It is in the URL at all only because an email link has no other carrier — so it is single-use, short-lived, and stripped from the address bar on arrival. A URL is written to server logs, browser history and referrer headers.
/collection | The Collection | gateway | gateway | public | yes | AS-01 | The Gateway Grid | Built | GatewayGrid | gateway
/collective/gallery | The Evidence Portfolio | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Evidence | publicpages |  |  |  | PUB.08. Ships empty: every plate must say whether it is a photograph, a render or a drawing, and a portfolio of renders shown as photographs is the commonest misrepresentation in this industry. /gallery (AS-09) is a property gallery and is a different thing; both are retained.
/collective/operators | The Operators | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Operators | publicpages |  |  |  | PUB.06 — what runs a property, and who is accountable when it does not.
/collective/partners | The Foundation | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Partners | publicpages |  |  |  | PUB.05 — the independent firms. Ships with functions stated and holders withheld until each engagement is recorded against the vehicle it serves.
/collective/press | The Wire | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Wire | publicpages |  |  |  | PUB.10 — external coverage. Ships empty and says so; the wireframe's six clippings were quotes attributed to real publications that have not published them.
/communique/request | Request the Dossier | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Dossier | publicpages |  |  |  | PUB.07 — the intelligence pack. What requesting it creates is stated above the form.
/gallery | Gallery | gateway | gateway | public | yes | AS-09 | The Gallery Frame | Built | Gallery | gatewaypages
/how-it-works | How It Works | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | HowItWorks | publicpages |  |  |  | PUB.02 / PUB.11 — the doctrine, then a hard cut to the arithmetic. Distinct from /how-capital-works, which is the waterfall itself rather than the argument for it.
/journal | The Journal | gateway | gateway | public | yes | AS-30 | The Journal | Built | JournalIndex | documents |  |  |  | Index. Entries newest first; the order is checked at load.
/journal/[slug] | Journal Entry | gateway | gateway | public | yes | AS-30 | The Journal | Built | JournalEntry | documents |  | slug |  | One entry. Figures are read from the registries, never typed into the prose.
/legal | Legal | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | DocumentIndex | documents |  |  |  | Index of the standing documents.
/legal/accessibility | Accessibility Statement | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents |  |  |  | States what has been tested and what has not. Currently: contrast computed, no assistive-technology testing performed.
/legal/complaints | Complaints Procedure | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents
/legal/cookies | Cookie Notice | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents
/legal/disclosures | Standing Disclosures | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents |  |  |  | Capital at risk, past performance, no guarantee. Body size, reading tone.
/legal/privacy | Privacy Notice | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents
/legal/terms | Terms and Conditions | gateway | gateway | public | yes | AS-29 | The Standing Document | Built | StandingDoc | documents
/maintenance | Maintenance | gateway | gateway | public | yes | AS-15 | System Status | Built | Composed | compose
/portfolio | The Portfolio | gateway | gateway | public | yes | AS-07 | The Portfolio Narrative | Built | Portfolio | gatewaypages
/roles | Open Roles | gateway | gateway | public | yes | AS-18 | Recruitment | Built | Roles | gatewaypages
/roles/[code] | Role | gateway | gateway | public | yes | AS-18 | Recruitment | Built | RoleDetail | gatewaypages |  | code
/search | Search | gateway | gateway | identified | no |  |  | Built | Composed | compose |  |  | Results are scoped to what the viewer may see, which requires knowing who they are. An anonymous search would either return nothing or leak the index.
/signal | The Signal | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Signal | publicpages |  |  |  | PUB.09 — the weekly transmission. No tuner gate; the form is simply present.
/space | Space | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Space | publicpages |  |  |  | The physical product: what is built, from what, and what it takes to keep standing.
/status | System Status | gateway | gateway | public | yes | AS-15 | System Status | Built | Composed | compose
/story | Story | gateway | gateway | public | yes | AS-08 | The Story Playback | Built | Story | gatewaypages
/structure | The Vehicle | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Structure | publicpages |  |  |  | From the PUB.01 footer, which calls it SPV Structure. The constitutional default is an LLP; an SPV needs Board approval per property, and the page says so.
/time | Time | gateway | gateway | public | yes | AS-32 | The Public Surface | Built | Time | publicpages |  |  |  | Entitlement: what it is, what it is not, and when it begins. The wireframe's exchange console is stated as unbuilt rather than described as though it exists.
/voices | Voices | gateway | gateway | public | yes | AS-24 | Testimonials | Built | Testimonials | gateway |  |  |  | Testimonials. No figure, no return, no performance reference — regulated speech.
/collection/[property] | Property | space | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property
/collection/[property]/capital | Capital | space | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property |  | The Capital LENS at the space vantage. Renders AP-03 and routes to the console; it does not render console disclosure because a tab is labelled Capital.
/collection/[property]/gallery | Gallery | space | space | public | yes | AS-10 | The Gallery Strip | Built | Composed | compose |  | property
/collection/[property]/location | Location | space | space | public | yes | AS-12 | Location Intelligence | Built | Composed | compose |  | property
/collection/[property]/space | Space | space | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property
/collection/[property]/time | Time | space | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property
/flow | SlowSpace Coastal | space | space | public | yes |  |  | Built | Offering | flow |  |  |  | Step 1 of 5. The offering at the space vantage: capital stack, six-stage waterfall, governance and programme, each carrying its confidence class.
/capital | Capital Console | capital | capital | office | no | AS-02 | The Property Console | Built | Composed | compose | portfolio.manage
/capital/calls | Capital Calls | capital | member | member | no | AS-26 | The Capital Call | Built | Composed | compose | capital.call
/capital/distributions | Distributions | capital | capital | office | no | AS-02 | The Property Console | Built | Composed | compose | distribution.execute
/capital/distributions/[ref] | Distribution | capital | capital | office | no | AS-02 | The Property Console | Built | Composed | compose | distribution.execute | ref
/capital/offerings | Offerings | capital | capital | office | no | AS-02 | The Property Console | Built | Composed | compose | offering.open
/capital/properties | Properties | capital | capital | office | no | AS-02 | The Property Console | Built | Composed | compose | portfolio.manage
/capital/properties/[id] | Property Console | capital | capital | office | no | AS-02 | The Property Console | Built | Composed | compose | portfolio.manage | id
/capital/properties/[id]/programme | Programme | capital | capital | office | no | AS-11 | The Stage Progression | Built | Composed | compose | property.advance_lifecycle | id
/capital/properties/[id]/valuations | Valuations | capital | capital | office | no | AS-02 | The Property Console | Built | Composed | compose | valuation.record | id
/capital/risk | Risk Register | capital | capital | office | no | AS-28 | The Risk Register | Built | Composed | compose | compliance.record
/capital/waterfall | Waterfall | capital | capital | office | no | AS-04 | The Capital Explainer | Built | CapitalExplainer | gateway | distribution.execute
/commit/[offering] | Commit | capital | capital | accredited | no | AS-06 | The Commitment Flow | Built | Composed | compose |  | offering | An Investor commits BEFORE membership exists — the Member Law fires on settlement, not here. Requiring member access would make it unreachable by anyone who could use it.
/commit/[offering]/execute | Execute | capital | capital | accredited | no | AS-19 | The Ledger Lock | Built | Composed | compose |  | offering | The execution sequence for a commitment made before membership exists.
/commit/[offering]/risk | Risk Disclosure | capital | capital | accredited | no | AS-14 | The Risk Disclosure | Built | Composed | compose |  | offering | The gate immediately before commitment, on the same path and for the same reason.
/flow/commit | Commit | capital | capital | public | yes |  |  | Built | Commit | flow |  |  | A worked demonstration of the whole arc, on illustrative data for a fictional partner rather than a real position. Public because the point is that a prospective investor can see every step - including the accreditation and disclosure they would meet later - before committing to any of it. | Step 4. The piston, 3000ms linear. States Committed, never Member.
/flow/risk | Risk Disclosure | capital | capital | public | yes |  |  | Built | RiskDisclosure | flow |  |  | A worked demonstration of the whole arc, on illustrative data for a fictional partner rather than a real position. Public because the point is that a prospective investor can see every step - including the accreditation and disclosure they would meet later - before committing to any of it. | Step 3. Seven clauses in severity order, on paper. The gate opens on reaching the end by any route.
/how-capital-works | How Capital Works | capital | capital | public | yes | AS-04 | The Capital Explainer | Built | CapitalExplainer | gateway |  |  | The waterfall explainer is the single most important thing a prospective investor can read before committing, and putting it behind a sign-in would mean the disclosure only reaches people who have already decided.
/legal/risk-disclosure | Risk Disclosure | capital | capital | public | yes | AS-14 | The Risk Disclosure | Built | StandingDoc | documents |  |  | It gates commitment, and it is also the document a prospective investor most needs to read before deciding whether to start. Public to read; the ACKNOWLEDGEMENT still requires identity and is recorded against a version.
/member/entitlement | Entitlement | time | time | member | no | AS-25 | The Time Ledger | Built | Composed | compose
/member/entitlement/[year] | Entitlement Year | time | time | member | no | AS-25 | The Time Ledger | Built | Composed | compose |  | year
/flow/accreditation | Accreditation | member | member | public | yes |  |  | Built | Accreditation | flow |  |  | A worked demonstration of the whole arc, on illustrative data for a fictional partner rather than a real position. Public because the point is that a prospective investor can see every step - including the accreditation and disclosure they would meet later - before committing to any of it. | Step 2. PR-01, resumable - each field saves on blur to a draft record.
/flow/settled | Settled | member | member | public | yes |  |  | Built | Settled | flow |  |  | A worked demonstration of the whole arc, on illustrative data for a fictional partner rather than a real position. Public because the point is that a prospective investor can see every step - including the accreditation and disclosure they would meet later - before committing to any of it. | Step 5. The first screen where the Member Law has fired.
/member | Your Position | member | member | member | no | AS-05 | The Member Console | Built | Composed | compose
/member/calibration | Unit Calibration | member | member | member | no | AS-33 | The Member Surface | Built | Calibration | memberpages |  |  |  | MEM.05. Every control is real and none can be transmitted: the property is at pre-construction, so there is no management system to reach.
/member/calls | Capital Calls | member | member | member | no | AS-26 | The Capital Call | Built | Composed | compose
/member/calls/[ref] | Capital Call | member | member | member | no | AS-26 | The Capital Call | Built | Composed | compose |  | ref |  | Default consequences render in full above the payment control.
/member/codex | The Codex | member | member | member | no | AS-33 | The Member Surface | Built | Codex | memberpages |  |  |  | MEM.07. The manual for one property. The conduct-linked forced buyback the source specifies is marked as not drafted and not in force.
/member/distributions | Distributions | member | member | member | no | AS-05 | The Member Console | Built | Composed | compose
/member/distributions/[ref] | Distribution | member | member | member | no | AS-05 | The Member Console | Built | Composed | compose |  | ref
/member/documents | Documents | member | member | member | no | AS-05 | The Member Console | Built | Composed | compose
/member/documents/[id] | Document | member | member | member | no | AS-05 | The Member Console | Built | Composed | compose |  | id
/member/holdings | Holdings | member | space | public | yes | AS-10 | The Gallery Strip | Built | Composed | compose
/member/holdings/[property] | Holding | member | space | public | yes | AS-03 | The Property Masthead | Built | PropertyMasthead | gateway |  | property
/member/notifications | Notifications | member | member | member | no |  |  | Built | Composed | compose |  |  |  | The alert centre. A system ticker (SIGNAL_APERTURE) never lands here; only things asked of the member do.
/member/pass | Access Credentials | member | member | member | no | AS-33 | The Member Surface | Built | Pass | memberpages |  |  |  | MEM.08. Issuing spends your nights and puts the visitor's conduct on your record.
/member/position | Position | member | member | member | no | AS-05 | The Member Console | Built | Composed | compose
/member/profile | Passport | member | member | member | no | AS-33 | The Member Surface | Built | Passport | memberpages
/member/reports | Reports | member | member | member | no | AS-05 | The Member Console | Built | Composed | compose
/member/resolutions | Resolutions | member | member | member | no | AS-33 | The Member Surface | Built | Boardroom | memberpages
/member/resolutions/[ref] | Ballot | member | member | member | no | AS-27 | The Ballot | Built | Composed | compose |  | ref |  | Sealed at every vantage. The confirmation never echoes the choice.
/member/settings | Settings | member | member | member | no |  |  | Built | Composed | compose
/member/settings/notifications | Notification Settings | member | member | member | no |  |  | Built | Composed | compose
/member/settings/security | Security | member | member | member | no |  |  | Built | Composed | compose
/member/settings/tax | Tax Details | member | member | member | no |  |  | Built | Composed | compose
/member/signal | The Signal | member | member | member | no | AS-33 | The Member Surface | Built | SignalLog | memberpages |  |  |  | MEM.06. A written, asynchronous record with the operating partner. No presence indicator and no typing state — both promise an immediacy the queue does not have.
/passport | Your Passport | member | member | identified | no |  |  | Built | Composed | compose |  |  | The passport is how someone BECOMES a member. Requiring membership to reach it would close the only door into the system.
/passport/accreditation | Passport · accreditation | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/address | Passport · address | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/annual-review | Passport · annual review | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/decision | Passport · decision | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/discover | Passport · discover | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system. | Stage 1 of 16. Resumable — each field autosaves on blur to a draft record, which is what makes PR-01 genuinely resumable rather than a second mechanism.
/passport/documents | Passport · documents | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/eligibility | Passport · eligibility | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/identity | Passport · identity | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/issued | Passport · issued | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/profile | Passport · profile | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/review | Passport · review | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/risk-profile | Passport · risk profile | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/screening | Passport · screening | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/source-of-funds | Passport · source of funds | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/suitability | Passport · suitability | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/passport/tax-residency | Passport · tax residency | member | capital | identified | no | AS-06 | The Commitment Flow | Built | Composed | compose |  |  | Accreditation is reached before membership exists, by definition — the Member Law fires on settlement, and settlement cannot happen until accreditation has. Requiring member access here would close the only door into the system.
/admin | Administration | admin | admin | office | no |  |  | Built | Composed | compose | organization.register
/admin/authority | Authority | admin | admin | office | no |  |  | Built | Composed | compose | authority.grant
/admin/authority/grants | Grants | admin | admin | office | no |  |  | Built | Composed | compose | authority.grant
/admin/authority/revocations | Revocations | admin | admin | office | no |  |  | Built | Composed | compose | authority.revoke
/admin/compliance | Compliance | admin | admin | office | no |  |  | Built | Composed | compose | compliance.record
/admin/compliance/accreditation | Accreditation Queue | admin | admin | office | no |  |  | Built | Composed | compose | accreditation.grant
/admin/compliance/conflicts | Conflict Register | admin | admin | office | no |  |  | Built | Composed | compose | conflict.disclose
/admin/compliance/events | Compliance Events | admin | admin | office | no |  |  | Built | Composed | compose | compliance.record
/admin/content | Content | admin | admin | office | no | AS-34 | The Admin Surface | Built | ContentAdmin | adminpages | content.publish |  |  | Every content class, its source, whether it binds and whether it is versioned.
/admin/failure | Constitutional Failure | admin | admin | office | no |  |  | Built | Composed | compose | constitutional_failure.declare |  |  | CF-01..CF-06. The gravest surface in the system and the least used. Declaring a failure requires a resolution reference, not a role — there is no login that can do this alone.
/admin/governance | Governance | admin | admin | office | no |  |  | Built | Composed | compose | resolution.table
/admin/governance/committees | Committees | admin | admin | office | no |  |  | Built | Composed | compose | committee.constitute
/admin/governance/policies | Policies | admin | admin | office | no |  |  | Built | Composed | compose | policy.approve
/admin/governance/resolutions | Resolutions | admin | member | member | no | AS-27 | The Ballot | Built | Composed | compose | resolution.table
/admin/governance/resolutions/[ref] | Resolution | admin | member | member | no | AS-27 | The Ballot | Built | Composed | compose | resolution.resolve | ref |  | Results only. Admin is NOT an exception to I-05 — it is the vantage most likely to assume it is.
/admin/ledger | Ledger | admin | admin | office | no |  |  | Built | Composed | compose | capital.deploy
/admin/media | Media | admin | admin | office | no | AS-34 | The Admin Surface | Built | MediaAdmin | adminpages | media.manage |  |  | Three kinds, required at registration with no default. A render registered as a photograph is a misrepresentation that needs no words.
/admin/reports | Reports | admin | admin | office | no |  |  | Built | Composed | compose | report.publish
/admin/research | Research | admin | admin | office | no |  |  | Built | Composed | compose | diligence.complete
/admin/telemetry | Telemetry | admin | admin | office | no |  |  | Built | Composed | compose | portfolio.manage
/admin/vehicles | Vehicles | admin | admin | office | no | AS-13 | The LLP Docket | Built | Composed | compose | vehicle.form
/admin/vehicles/[llpin] | Docket | admin | admin | office | no | AS-13 | The LLP Docket | Built | Composed | compose | vehicle.form | llpin
/admin/vehicles/[llpin]/audit | Docket Audit | admin | admin | office | no | AS-13 | The LLP Docket | Built | Composed | compose | compliance.record | llpin
/admin/vehicles/[llpin]/charges | Charges | admin | admin | office | no | AS-13 | The LLP Docket | Built | Composed | compose | vehicle.form | llpin
/admin/vehicles/[llpin]/filings | Statutory Calendar | admin | admin | office | no | AS-13 | The LLP Docket | Built | Composed | compose | compliance.record | llpin
/admin/vehicles/[llpin]/formation | Formation | admin | admin | office | no | AS-13 | The LLP Docket | Built | Composed | compose | vehicle.form | llpin
/admin/vehicles/[llpin]/partners | Register of Partners | admin | admin | office | no | AS-13 | The LLP Docket | Built | Composed | compose | vehicle.form | llpin
/admin/vehicles/[llpin]/resolutions | Resolutions | admin | admin | office | no | AS-13 | The LLP Docket | Built | Composed | compose | resolution.table | llpin
/admin/vehicles/new | Form a Vehicle | admin | admin | office | no | AS-34 | The Admin Surface | Built | VehicleFormation | adminpages | vehicle.form |  |  | Eight stages. Two irreversible, two gated on Board approval. §24a: the LLP is the default and any other legal form needs a resolution naming the specific property.

## Popups
Pop-ups, Modals & Dialogs
Two are built. The rest are proposed — read the Source column before treating any row as agreed. Every modal in this system closes on Escape AND on the backdrop, and its close control says Close, never Agree: a dialog whose only exit is 'I agree' collects consent from people trying to get rid of it.
ID | Where | Trigger | What it does | Ground | Status | Source | Notes
P-01 | /flow/accreditation | Read the Terms and Conditions button | Renders the full T&C document over the form. Gates the agreement checkbox — the box enables only once the document has been opened. | Paper | Built | Code | app/_assemblies/flow.tsx:577. Opens IN PLACE rather than linking away: a link loses the half-filled application. Does NOT require scrolling to the end — scroll position is not reading, and a keyboard user never fires a scroll handler.
P-02 | /gallery | Click a frame | Lightbox. Arrow keys step, Escape closes, close control always visible. | Void | Built | Code | app/_assemblies/gatewaypages.tsx:229. Close is never hover-revealed and never in a vanishing corner.
P-03 | All pages | First visit | Cookie / consent banner. | Paper | Not built | Proposed | /legal/cookies exists as a document with no banner in front of it. REQUIRED for DPDP and GDPR if you take EU traffic. Must default to declining non-essential.
P-04 | /flow/accreditation | Navigating away mid-form | Unsaved-changes guard. | Paper | Not built | Proposed | The form autosaves on blur, so this is lower risk than usual — but a half-finished PAN field is lost on a back button today.
P-05 | Any authenticated surface | Session nearing expiry | Session-expiry warning with an extend control. | Paper | Not built | Proposed | Blocked: no authentication exists. Build with Clerk, not before.
P-06 | /member/resolutions | Cast a vote | Vote confirmation. Contribution-weighted, irreversible, and states the weight being cast. | Paper | Not built | Proposed | A vote is irreversible under §24a. It needs the same deliberation treatment as the commitment piston, not an OK button.
P-07 | /admin/media | Upload | File picker with type, dimension and licence capture. | Paper | Not built | Proposed | The media admin surface is built; the upload path is not. Blocked on Vercel Blob.
P-08 | /admin/vehicles/new | Submit formation | Confirm-before-create for a new LLP. | Paper | Not built | Proposed | Creates a constitutional entity. Should require a resolution reference, not a click.
P-09 | Global | A destructive admin action | Confirm-destructive dialog. Types the object name to confirm. | Paper | Not built | Proposed | No destructive admin action is wired yet, so nothing is at risk today.
P-10 | /flow/commit | — | NONE, deliberately. | — | N/A | Code | The commitment is a 3-second sustained press (the piston), not a dialog. The duration IS the deliberation. A confirm dialog after a hold would be two confirmations, which trains people to dismiss both.

## Notifications
In-Product Notifications
Two routes exist to HOLD notifications; no notification is generated by anything. Every row below is Proposed unless marked otherwise. The trigger column names the event — a notification without a named event is a notification nobody can test.
ID | Event that fires it | Message | Audience | Urgency | Where it lands | Status | Source | Notes
N-00 | — | (the surfaces that hold them) | Member | — | /member/notifications, /member/settings/notifications | Scaffold | Code | Both routes exist and render the registry Surface. Nothing writes to them.
N-01 | Accreditation submitted | Application received. A decision follows within 15 working days. | Applicant | Normal | Email + in-product | Not built | Proposed | PR-01 states the window; nothing currently confirms receipt.
N-02 | Accreditation decided | Accreditation approved / declined, with the reason. | Applicant | High | Email + in-product | Not built | Proposed | A decline must state a reason and a route to appeal.
N-03 | Deposit received | ₹50,000 received. It holds your position; it does not make you a partner. | Investor | High | Email + in-product | Not built | Proposed | Must repeat the Member Law. The commonest misreading of a deposit is that it completes the purchase.
N-04 | Completion window opening | Balance and Vehicle Agreement due within 15 working days. | Investor | High | Email | Not built | Proposed | Needs a countdown, and a second at T-3 days.
N-05 | SETTLEMENT | You are a Member of <vehicle>. Entitlement and governance rights begin now. | Member | Critical | Email + in-product | Not built | Proposed | THE MEMBER LAW (I-08) fires here and only here. This is the single most important notification in the system and it is irreversible.
N-06 | Resolution opened | A resolution is open for your vote. Threshold: ordinary / special. Closes <date>. | Member | High | Email + in-product | Not built | Proposed | Must state the threshold and the voting weight, per §24a.
N-07 | Resolution closing | Your vote has not been cast. Voting closes in 48 hours. | Member | High | Email + in-product | Not built | Proposed | A tie is NOT approval, so an uncast vote has a real consequence and the reminder must say so.
N-08 | Resolution decided | Outcome, the count, and the threshold it met. | Member | Normal | Email + in-product | Not built | Proposed | ADR-0008: secret ballot, transparent outcome. Publish the tally, never who voted how.
N-09 | Distribution declared | <amount> declared for the period ending <date>. | Member | Normal | Email + in-product | Not built | Proposed | Must carry a confidence class like every other figure.
N-10 | Distribution paid | <amount> paid to the account ending <n>. | Member | Normal | Email + in-product | Not built | Proposed
N-11 | Distribution BLOCKED | No distribution this period. Stage six does not run if the reserve would fall below its floor. | Member | High | Email + in-product | Not built | Proposed | Silence here reads as an error. A profitable period with no distribution is normal and must be explained when it happens, not in a FAQ.
N-12 | Entitlement opens | Your <n> nights for <year> are now drawable. | Member | Normal | In-product | Not built | Proposed | Not before handover — nothing is drawable against an unbuilt asset.
N-13 | Entitlement expiring | <n> nights lapse on <date>. | Member | Normal | Email + in-product | Not built | Proposed | Needs a stated lapse policy first — see Decisions D-07.
N-14 | Document version changed | <document> is now v<n>. What changed: <summary>. | Member | High | Email | Not built | Proposed | A binding document changing under someone silently is the failure mode. Must link the diff.
N-15 | Covenant proximity | DSCR approaching the covenant threshold. | Office | Critical | In-product | Not built | Proposed | Office vantage only. Never shown at member vantage without Board sign-off on the wording.
N-16 | Valuation published | <property> revalued to <amount> by <source>. | Member | Normal | In-product | Not built | Proposed | Must name the source and its confidence class; a management estimate is not an appraisal.
N-17 | Lead captured | A signal / dossier request arrived. | Office | Low | Email | Live | Code | The only notification that actually fires today. app/api/signal, app/api/dossier → lib/leads.ts.

## Emails
Transactional Email
Two endpoints are live via Resend; both return 503 without RESEND_API_KEY and the page says so rather than showing a false success. Everything else is proposed. No template system, no unsubscribe handling and no verified sending domain exists yet.
ID | Trigger | To | Subject / purpose | Type | Template | Status | Source | Notes
E-01 | /signal form submit | SIGNAL_LEAD_EMAIL | New Signal subscriber | Internal | Plain text | Live | Code | lib/leads.ts. Returns 503 when unconfigured; the form renders an honest failure with a mailto fallback.
E-02 | /communique/request submit | DOSSIER_LEAD_EMAIL | New dossier request | Internal | Plain text | Live | Code | Same path. 400 on invalid input, 503 on unconfigured.
E-03 | Signal form submit | The subscriber | Confirm the subscription (double opt-in) | Outbound | — | Not built | Proposed | REQUIRED. Today you capture an address and send that person nothing — no confirmation and no way to unsubscribe. This is a compliance gap, not a nicety.
E-04 | Dossier request | The requester | The dossier itself | Outbound | — | Not built | Proposed | The form promises an intelligence pack. Nothing sends one. See Assets A-20.
E-05 | Sign-up | New account | Verify your email address | Outbound | — | Not built | Proposed | Blocked on Clerk, which handles this natively.
E-06 | Accreditation submitted | Applicant | Application received · 15 working days | Outbound | — | Not built | Proposed | Pairs with N-01.
E-07 | Accreditation decided | Applicant | Decision, with reason | Outbound | — | Not built | Proposed | Pairs with N-02.
E-08 | Deposit received | Investor | ₹50,000 received · what it does and does not do | Outbound | — | Not built | Proposed | Must state that a deposit makes nobody a partner.
E-09 | Deposit received | Investor | Payment receipt (GST-compliant) | Outbound | — | Not built | Proposed | Tax-document requirements unconfirmed — see Decisions D-05.
E-10 | Settlement | Member | You are a Member of <vehicle> | Outbound | — | Not built | Proposed | THE MEMBER LAW. Should carry the Vehicle Agreement and the register entry as attachments.
E-11 | Resolution opened | Members | A resolution is open · closes <date> | Outbound | — | Not built | Proposed
E-12 | Resolution closing | Non-voters | Voting closes in 48 hours | Outbound | — | Not built | Proposed
E-13 | Resolution decided | Members | Outcome and tally | Outbound | — | Not built | Proposed | Tally yes; individual votes never.
E-14 | Distribution paid | Member | Distribution statement | Outbound | — | Not built | Proposed | Needs a PDF generator — none exists.
E-15 | Quarterly | Members | Vehicle report | Outbound | — | Not built | Proposed | Cadence and content not agreed — Decisions D-08.
E-16 | Document version change | Members | <document> updated to v<n> | Outbound | — | Not built | Proposed | Legally significant. Must link the diff, not just announce it.
E-17 | Weekly | Signal subscribers | The Signal | Marketing | — | Not built | Proposed | Needs unsubscribe, preference centre and a verified domain before a single send.
E-18 | Password reset | Account | Reset your password | Outbound | — | Not built | Proposed | Blocked on Clerk.

## Gaps
Current Gaps
What is missing, why it matters, and what it blocks. Severity is my assessment. 'Blocks launch' means I would not put the URL in front of an investor until it is closed.
ID | Area | The gap | What it blocks | Severity | Effort | Status | Source | Notes | Codex category | Codex tier | Codex accountable owner | Codex required action | Codex closure evidence | Codex gate
G-01 | Legal | ~9,000 words of Terms and Risk Disclosure have never been reviewed by a lawyer. | Any real investor traffic | Blocks launch | External | Open | Code | content/legal.ts + slowspace.ts. Drafted to be accurate; not drafted to be relied on. This is the single largest exposure on this sheet and it is not a code problem. | Launch Blockers | Tier 1 | Founders / Legal | Engage qualified counsel; freeze public legal text until reviewed and approved. | Counsel sign-off, controlled document versions, and publication authorization recorded. | G0 · Legal boundary
G-02 | Legal | Repository is PUBLIC, so the unreviewed copy and the LLP identifiers are world-readable. | — | Blocks launch | Minutes | Open | Code | One command flips it. Raised twice; not yet actioned. | Launch Blockers | Tier 1 | Founders / Engineering | Remove public access to drafts, identifiers, and internal logic; approve a publication policy. | Repository/access review and written publication approval. | G0 · Legal boundary
G-03 | Entity | SlowSpace Coastal LLP, LLPIN AAC-4471 and the Udupi registered office are modelled from a dossier, not verified against the MCA register. | Publishing the offering | Blocks launch | External | Open | Code | If the entity is not incorporated with that identifier, the platform is asserting that it is. | Launch Blockers | Tier 1 | Legal | Verify every published entity fact from independent authoritative records. | Verification log with source, verifier, date, expiry, and approved public wording. | G0 · Legal boundary
G-04 | Auth | No authentication. lib/access.ts fails closed, so 63 member/office routes correctly deny everyone. | Every member and office surface | High | Large | Open | Code | Deliberate and correct for an unfinished system. Clerk is chosen but not integrated. | Launch Blockers | Tier 1 | Engineering | Implement production authentication with session expiry, revocation, and protected-route tests. | End-to-end identity and protected-route test evidence in production-like environment. | G1 · Safe entry
G-05 | Data | No database. Every page reads static TypeScript. | Persistence of anything | High | Large | Open | Code | Drizzle schema and 27 tables are generated and checked; nothing connects to Neon. | Launch Blockers | Tier 1 | Engineering | Connect the governed schema to production persistence; replace static operational state. | Migration record, backup/restore evidence, and record lifecycle test. | G2 · Governed transaction
G-06 | Payments | No payment processor. The ₹50,000 deposit cannot be taken. | The commitment flow | High | Large | Open | Code | Razorpay chosen. The piston records a state change in memory and nothing else. | Launch Blockers | Tier 1 | Engineering + Finance | Implement verified settlement and reconciliation before any commitment or capital-call action is exposed. | Success/failure/reconciliation tests plus an owned support and reversal runbook. | G2 · Governed transaction
G-07 | Product | CLOSED 1 Aug 2026: all 82 scaffolds now render composed pages through the composition layer (app/_assemblies/compose.tsx) — 11 section primitives over the existing design system, every page carrying the four-stage disclosure strip (Public / Post-KYC / Post-commitment / Operational). | — | Closed | — | Closed | Code | Remaining depth is data, not pages: operational registers state their absence honestly until persistence exists. | Product Completeness | Tier 3 | Product + Engineering | Maintain the closed composition-layer evidence; review public scope before broad launch. | Route inventory confirms each exposed public surface is functional or clearly disclosed. | G4 · Launch candidate
G-08 | Media | No photography exists. The gallery ships five labelled drawings. | Every visual surface | High | External | Open | Code | content/gateway.ts states this plainly rather than shipping renders as photographs. See the Assets sheet. | Product Completeness | Tier 3 | Brand + Legal | Publish only licensed, consented imagery with accurate render/drawing labels. | Asset register covers licence, consent, provenance, label, approver, and expiry. | G4 · Launch candidate
G-09 | Ops | No error tracking. | Knowing when production breaks | High | Small | Open | Doc | Sentry identified as the sixth account; not opened. | Platform Readiness | Tier 2 | Engineering | Configure error reporting, alert ownership, and escalation for production failures. | Deliberate-error test reaches the accountable on-call owner. | G3 · Reliable runtime
G-10 | Ops | No rate limiting on /api/signal or /api/dossier. | Publicising the URL | High | Small | Open | Code | Both are public, unauthenticated and send email. Trivially abusable once the domain is known. | Launch Blockers | Tier 1 | Engineering | Rate-limit all public email/form endpoints and alert on abuse patterns. | Automated rate-limit/rejection tests and documented alert thresholds. | G1 · Safe entry
G-11 | Compliance | No cookie/consent banner, no unsubscribe, no double opt-in. | EU traffic; any marketing send | High | Medium | Open | Code | /legal/cookies documents a policy nothing enforces. | Launch Blockers | Tier 1 | Legal + Product | Implement recorded consent, preference handling, unsubscribe, and applicable marketing controls. | Consent record, unsubscribe test, and policy-to-implementation review. | G1 · Safe entry
G-12 | Ops | No CI. npm run verify runs only via a local pre-commit hook, which --no-verify walks past. | Confidence in main | Medium | Small | Open | Code | GitHub Actions workflow not yet added; the token scope for it exists. | Platform Readiness | Tier 2 | Engineering | Establish protected CI/CD with required checks, deployment approval, and rollback. | Build/test/preview/release logs and a successful rollback exercise. | G3 · Reliable runtime
G-13 | Product | Notifications: two routes hold them, nothing generates one. | Every member communication | Medium | Medium | Open | Code | See the Notifications sheet. | Product Completeness | Tier 3 | Product + Engineering | Generate regulated and operational notifications with traceable delivery and preference logic. | Delivery records, preference tests, and resend/escalation path evidence. | G4 · Launch candidate
G-14 | Product | No PDF generation. | Statements, receipts, the dossier | Medium | Medium | Open | Proposed | Referenced by four proposed emails. | Product Completeness | Tier 3 | Product + Engineering | Generate versioned PDFs/receipts with retention and retrieval controls. | Representative outputs reviewed; version, retention, and retrieval test passes. | G4 · Launch candidate
G-15 | Design | Risk categories: 8 in the design system, 10 in the registry. Six render neutral grey. | Correct risk colour | Medium | Small | Open | Doc | WAVE-5-OPEN-QUESTIONS A2. riskColour() falls back to steel and a test pins that. | Operational Maturity | Tier 4 | Product + Legal | Approve one risk taxonomy and reconcile registry, UI, legal material, and operations. | Cross-surface taxonomy review signed by Product and Legal. | G4 · Launch candidate
G-16 | Design | Brand voice conflict: L1-02 says 'Warm', Addendum A says 'never persuades'. | Consistent copy | Low | Small | Open | Doc | WAVE-5 A1. Resolved in practice toward plain and non-blaming; not written down. | Operational Maturity | Tier 4 | Brand + Product | Write the hierarchy between brand narrative and interface voice; apply it to critical paths. | Approved copy principle and sample review of public, transactional, and failure states. | G4 · Launch candidate
G-17 | Content | /collective/press and /collective/gallery ship empty on purpose. | Credibility surfaces | Low | External | Open | Code | The wireframe's six press clippings were quotes attributed to publications that have not published them. Empty and honest beats populated and false. | Product Completeness | Tier 3 | Brand + Legal | Keep empty states explicit until verified press/gallery material exists; never invent social proof. | Publication inventory with source approval and required content labels. | G4 · Launch candidate
G-18 | Ops | Vercel region pinned to bom1 for DPDP residency; plan support unverified. | First deploy | Low | Minutes | Open | Code | vercel.json. Will fail the deploy if the plan disallows region pinning. | Platform Readiness | Tier 2 | Engineering + Operations | Verify host plan/region support and complete a production deployment smoke test. | Provider confirmation, environment separation checklist, smoke test, and rollback proof. | G3 · Reliable runtime
G-19 | Ops | No persistent immutable audit log covers ownership, payment, legal acknowledgement, or document access. | Disputed ownership, money movement, and legal evidence | High | Large | Open | Proposed | The domain model expresses audit intent, but the platform has no persisted append-only evidence trail. | Platform Readiness | Tier 2 | Engineering + Legal | Persist an immutable audit record for ownership, payment, legal acknowledgement, and document access. | Append-only audit record, retrieval test, access control, and retention policy evidence. | G2 · Governed transaction
G-20 | Auth | Authentication is not yet paired with an enforced production role/right/scope authorization model. | Any sensitive member or office action | High | Large | Open | Code | lib/authority.ts models rights and grants; route/runtime enforcement is not integrated with real identity. | Platform Readiness | Tier 2 | Engineering | Enforce role/right/scope authorization on every sensitive endpoint and operational action. | Negative authorization tests and periodic access-review record. | G1 · Safe entry
G-21 | Ops | No approved backup policy, restore test, RPO, or RTO exists for a future production database. | Recovery from data loss or provider failure | High | Medium | Open | Proposed | A database without a tested recovery objective is not a governed production system. | Operational Maturity | Tier 2 | Operations + Engineering | Define backup policy, restore testing, RPO, and RTO for production data. | Approved recovery policy and successful restore exercise measured against RPO/RTO. | G3 · Reliable runtime
G-22 | Ops | No production secret inventory, rotation ownership, expiry control, or audit process exists. | Secure operation of third-party integrations | High | Medium | Open | Proposed | Environment variables are documented, but production secret governance is not yet established. | Platform Readiness | Tier 2 | Engineering + Operations | Establish secret inventory, ownership, rotation, expiry, and audit controls. | Secret register and a documented, successful rotation exercise. | G3 · Reliable runtime
G-23 | Ops | No production monitoring covers uptime, latency, email/payment failures, or database health. | Early detection and timely response | High | Medium | Open | Proposed | Telemetry design exists, but it is not a monitored production control plane. | Platform Readiness | Tier 2 | Engineering + Operations | Monitor uptime, API latency, email/payment failures, and database health with alerts. | Dashboards, thresholds, alert routing, and weekly review evidence. | G3 · Reliable runtime
G-24 | Accessibility | No evidenced WCAG, keyboard, screen-reader, or contrast audit has been completed on launch-critical flows. | Accessible external use and reliable compliance posture | Medium | Medium | Open | Proposed | The design system declares accessibility contracts; independent flow-level verification remains required. | Operational Maturity | Tier 2 | Product + Engineering | Audit key flows for WCAG, keyboard, screen-reader, contrast, and reduced-motion behaviour. | Accessibility report; critical defects closed or formally accepted by the accountable owner. | G4 · Launch candidate
G-25 | Security | No recorded dependency, OWASP, CSP, security-header, or independent security review exists. | Trustworthy external use | High | Medium | Open | Proposed | Security design intent is not a substitute for a release evidence pack. | Platform Readiness | Tier 2 | Engineering + Security | Complete dependency, OWASP, CSP, security-header, and independent security review. | Risk report; critical findings closed or formally accepted before external scale. | G3 · Reliable runtime
G-26 | Performance | No approved and measured LCP, CLS, INP, bundle, image, or Lighthouse budgets exist. | Reliable public performance at launch | Medium | Small | Open | Proposed | The design system refers to performance contracts; platform-wide targets are still absent. | Platform Readiness | Tier 2 | Engineering + Product | Set measurable LCP, CLS, INP, bundle, image, and Lighthouse budgets. | Representative public and signed-in performance report meets approved budgets. | G3 · Reliable runtime
G-27 | Data governance | No approved retention, archival, deletion, erasure, or record-ownership policy governs production records. | Compliant data lifecycle management | High | Medium | Open | Proposed | Future persistence must not precede data-governance decisions. | Operational Maturity | Tier 2 | Legal + Operations | Define retention, archival, deletion, erasure, and data-record ownership. | Approved schedule and tested request workflow with accountable record owner. | G3 · Reliable runtime
G-28 | Business continuity | No rehearsed procedure exists for payment, email, database, cloud, or deployment rollback outage. | Orderly incident response and launch resilience | High | Medium | Open | Proposed | Runbooks must be owned and exercised before broad public traffic. | Operational Maturity | Tier 2 | Operations + Engineering | Create and rehearse continuity procedures for provider, database, cloud, email, payment, and rollback outages. | Current runbooks and recorded tabletop/rehearsal with fixes closed. | G3 · Reliable runtime

## Decisions
Decisions Awaiting You
Each is a decision I could not make for you because it is commercial, fiduciary, legal or a matter of taste. Where I had a defensible default I applied it and said so in My Recommendation — none of those is agreed. YELLOW CELLS ARE YOURS TO FILL.
ID | Area | The decision | My recommendation | Source | Your decision | Owner | Status | Due | Codex linked gaps | Codex decision rule | Codex required evidence | Codex launch impact | Codex next action | Codex recommended owner
D-01 | Legal | Engage a lawyer to review the Terms and Risk Disclosure before any real traffic. Who, and when? | Do this before the domain is public. Nothing else on this sheet costs more to get wrong. | Code |  |  | Open |  | G-01 | A named qualified counsel and written approval are required before public investor traffic. | Counsel engagement, reviewed redlines, approval/version record. | Public launch blocked until closed. | Name counsel, scope the review, and set a review deadline. | Founders / Legal
D-02 | Legal | Repository visibility: public or private? | Private until D-01 closes. Search engines cannot un-crawl. | Code |  |  | Open |  | G-02 | Default to private until legal and entity publication controls pass. | Repository visibility decision and completed sensitive-content inventory. | Public launch blocked until closed. | Approve private access or a documented sanitised-public scope. | Founders / Engineering
D-03 | Entity | Confirm SlowSpace Coastal LLP is incorporated, and the real LLPIN and registered office. | Replace with placeholders until confirmed, or confirm and keep. | Code |  |  | Open |  | G-03 | No legal entity fact may be published without independent verification. | Authoritative entity extract, verifier, date, and approved wording. | Public launch blocked until closed. | Provide the verification source and authorize the public record. | Legal
D-04 | Commercial | Minimum unit is 5% and the ceiling 50%. Confirm both. | Keep. 5% admits a wider register; 50% is where a partner would carry every ordinary resolution alone under §24a. | Code |  |  | Open |  | G-01 | Commercial terms must be legally reviewed before an external commitment is offered. | Approved minimum/maximum ownership terms in the legal document set. | Commitment launch blocked until reflected in approved terms. | Confirm the 5% / 50% policy or replace both values. | Founders + Legal
D-05 | Finance | Is the ₹50,000 deposit taxable on receipt, and what document must issue? | Needs your accountant. It changes E-09 and the receipt wording. | Proposed |  |  | Open |  | G-06, G-14 | Tax treatment and receipt obligations need an accountant’s written position before payment enablement. | Tax memo and approved receipt/invoice requirements. | Payments remain disabled until resolved. | Obtain accountant advice and choose the issuing document. | Finance + Legal
D-06 | Commercial | Confirm the entitlement pool of 180–210 nights a year for the whole property. | Keep. Derived so that no partition can exceed what the property can deliver. | Code |  |  | Open |  | G-01, G-13 | Entitlement policy must be explicit and match the approved terms, notifications, and member records. | Approved annual pool policy and capacity rationale. | Member launch scope constrained until resolved. | Confirm the annual entitlement range and owner for future review. | Founders + Product
D-07 | Commercial | Do unused nights lapse, roll over, or convert? | Needs a policy before N-13 can be written. Lapse is simplest and the least generous; say which it is. | Proposed |  |  | Open |  | G-01, G-13 | Unused-night treatment must be legally and operationally defined before member allocation rules ship. | Approved policy reflected in terms, notifications, and member settings. | Member feature incomplete until resolved. | Choose lapse, roll-over, or conversion; record effective date. | Founders + Legal
D-08 | Comms | Reporting cadence to members — quarterly, half-yearly? | Quarterly, aligned to the distribution period. | Proposed |  |  | Open |  | G-13 | Reporting cadence must be a service/communication commitment that operations can meet. | Approved cadence, owner, template, and escalation path. | Operational communications cannot be treated as complete until resolved. | Select cadence and accountable publisher. | Operations + Product
D-09 | Design | Risk categories: extend the design system to 10, or map the registry's 10 onto 8? | Map first (no amendment needed), then extend. | Doc |  |  | Open |  | G-15 | One risk taxonomy must govern code, legal text, and interface colour semantics. | Mapping table approved by Product and Legal. | Launch candidate gate cannot pass without resolution or formal deferral. | Approve mapping-first approach or authorize an amendment path. | Product + Legal
D-10 | Brand | Brand voice: does L1-02 'Warm' or Addendum A 'never persuades' govern interface copy? | Addendum A governs interface copy; L1-02 governs member-facing narrative. Write it down. | Doc |  |  | Open |  | G-16 | Interface and narrative copy need a written hierarchy, not an informal interpretation. | Approved voice rule and critical-path copy review. | Launch candidate gate cannot pass without resolution or formal deferral. | Ratify the proposed hierarchy or issue a replacement rule. | Brand + Product
D-11 | Ops | ANSWERED 1 Aug 2026: the domain is getawaycollective.co (www 301s to the apex). The code now carries it. REMAINING: the domain currently serves a GoDaddy Website Builder page — DNS must be repointed to Vercel at go-live, and the builder page retired. | Set NEXT_PUBLIC_SITE_URL=https://getawaycollective.co in Vercel. Decide the cutover moment: repointing DNS replaces the current GoDaddy page immediately. | Code |  |  | Open |  | G-18 | DNS cutover is a release decision: a production smoke test and rollback authority must exist first. | Approved cutover window, Vercel configuration, smoke test, rollback owner. | No broad launch before successful controlled cutover. | Choose the cutover window and name rollback authority. | Founders + Engineering
D-12 | Ops | Confirm the Vercel plan supports region pinning to bom1. | Needed for the DPDP residency claim. If not, either upgrade or drop the claim — do not keep the claim without the pinning. | Code |  |  | Open |  | G-18 | A data-residency claim must match the actual hosting plan and configuration. | Provider confirmation and environment configuration evidence. | Do not publish the residency claim until verified. | Confirm plan capability or remove/replace the claim. | Engineering + Legal
D-13 | Ops | Open a Sentry account (the sixth). | Yes, before launch. Silent production failures are the worst kind. | Doc |  |  | Open |  | G-09, G-23 | Error monitoring must have named on-call ownership and alert routing. | Configured account, test alert, escalation roster, and review cadence. | Reliable-runtime gate blocked until closed. | Open account, connect environments, and nominate on-call owner. | Engineering + Operations
D-14 | Media | Commission photography, or ship labelled drawings? | Ship drawings, labelled as drawings, until a property is photographable. Commission for Padubidri at handover. | Code |  |  | Open |  | G-08 | Only provenance-cleared media may replace labelled drawings. | Asset register and legal/brand approval for each published item. | Content remains intentionally sparse until evidence exists. | Choose labelled drawings now or approve a photography brief and budget. | Brand + Legal
D-15 | Product | Which of the 12 public scaffolds get built first? | See the IA sheet filtered to public + scaffold. They are indexable, so they are what a stranger finds. | Code |  |  | Open |  | G-07, G-17 | Public scope must be selected intentionally; unsupported public surfaces must stay explicit or unavailable. | Approved public route/content inventory with owners. | Launch candidate gate requires an approved public inventory. | Prioritise public routes by legal, transaction, and credibility impact. | Product + Engineering
D-16 | Comms | Verify a sending domain in Resend. | Required before any outbound email. The sandbox sender only delivers to your own address. | Code |  |  | Open |  | G-10, G-11 | Outbound email requires a verified sending domain, consent controls, unsubscribe, and abuse protection. | Verified domain plus end-to-end send, unsubscribe, and rate-limit tests. | Public email flows remain off until closed. | Verify domain and appoint communications owner. | Engineering + Operations
D-17 | Legal | Do you take EU traffic? It decides whether GDPR applies on top of DPDP. | Assume yes unless you geo-block. It changes P-03 and E-03. | Proposed |  |  | Open |  | G-11, G-27 | Traffic jurisdiction determines privacy obligations; assume the stricter case until a lawful restriction exists. | Written jurisdiction decision and updated privacy/retention controls. | External marketing scope constrained until resolved. | Confirm accepted jurisdictions or authorize a compliant geo-restriction. | Legal + Founders
D-18 | Domain | Ratify the §33 amendment queue: 10 candidate objects the vehicle domain model registers (see the Domain sheet). | Ratify OwnershipCalendar + AllocationRight first — Time is the only domain with zero ratified objects. FixedAsset and DebtFacility next; both are needed before the first fit-out invoice and the first covenant test. | Code |  |  | Open |  | G-05, G-19 | Constitutional amendments must precede persistence for newly material business objects. | Ratified amendment record and generated registry/schema evidence. | No data model extension outside ratified scope. | Prioritise the amendment queue through the constitutional process. | Founders + Governance
D-19 | Domain | Confirm the audit-threshold policy: the statutory mirror assumes EVERY GC vehicle crosses ₹25 lakh contribution at formation, so all are audited and ITR-5 falls on 31 October. | True of SlowSpace (₹4 Cr equity). Confirm it holds as standing policy so the mirror never needs a per-vehicle exception. | Code |  |  | Open |  | G-01, G-19 | Audit-threshold policy must be grounded in counsel/accountant advice and applied per entity where needed. | Approved statutory interpretation and vehicle applicability record. | Financial/legal reporting assumptions remain provisional until closed. | Confirm standing policy or define the per-vehicle exception process. | Finance + Legal
D-20 | Identity & access | Choose the production authentication provider, authorization model, and periodic access-review owner. | Use a provider with session revocation and implement rights/scope checks from the existing authority model. | Codex |  |  | Open |  | G-04, G-20 | Authentication and authorization must ship together; identity alone does not grant authority. | Provider selection, role/right/scope policy, negative tests, access-review schedule. | Safe-entry gate blocked until closed. | Approve provider and accountable access-review owner. | Founders + Engineering
D-21 | Audit | Approve the immutable audit-record scope, retention period, and retrieval authority. | Start with ownership, payment, legal acknowledgement, and document access; preserve append-only evidence. | Codex |  |  | Open |  | G-19 | Audit records must be immutable, scoped, retrievable, and retained by policy. | Approved scope/retention and a working append-only retrieval test. | Governed-transaction gate blocked until closed. | Approve scope, retention, and retrieval authority. | Legal + Engineering
D-22 | Disaster recovery | Approve RPO, RTO, backup frequency, restore-test cadence, and accountable owner. | Set conservative written objectives before persistence begins; test restore before external scale. | Codex |  |  | Open |  | G-21 | Recovery objectives must be explicit and tested, not implied by a hosting provider. | Approved RPO/RTO and successful restore drill. | Reliable-runtime gate blocked until closed. | Approve objectives and recovery owner. | Operations + Engineering
D-23 | Secrets | Choose the production secret store and approve rotation/expiry ownership. | Use managed secrets with inventory and scheduled rotation; never rely on unmanaged long-lived environment values. | Codex |  |  | Open |  | G-22 | Each production secret needs an owner, expiry/rotation rule, and audit trail. | Secret register and completed rotation drill. | Reliable-runtime gate blocked until closed. | Choose the managed store and owners. | Engineering + Operations
D-24 | Monitoring | Name the on-call owner and approve monitoring/alert thresholds for critical services. | Cover uptime, latency, email, payments, database health, and deployment failure from day one. | Codex |  |  | Open |  | G-09, G-23 | Monitoring is only operational when alerts reach a named responder with a documented escalation path. | Alert test, escalation roster, dashboard, and weekly review. | Reliable-runtime gate blocked until closed. | Name on-call and approve thresholds. | Operations + Engineering
D-25 | Accessibility | Approve the launch accessibility standard and the person authorized to accept residual risk. | Meet WCAG 2.2 AA on launch-critical flows; no critical keyboard or screen-reader defect remains open. | Codex |  |  | Open |  | G-24 | Accessibility requires independent flow-level evidence in addition to design-system intent. | WCAG 2.2 AA audit and critical-defect closure record. | Launch-candidate gate blocked until closed or formally scoped out. | Approve the standard and residual-risk authority. | Product + Engineering
D-26 | Security | Authorize an independent security review and decide who may accept any residual critical risk. | No critical vulnerability is accepted for public launch; evidence must cover OWASP, CSP, headers, and dependencies. | Codex |  |  | Open |  | G-25 | Security release acceptance must be based on evidence and a named risk accepter. | Security report with critical findings resolved. | Reliable-runtime gate blocked until closed. | Authorize review and residual-risk authority. | Founders + Engineering
D-27 | Performance | Approve measurable launch performance budgets and an exception owner. | Set LCP, CLS, INP, bundle, image, and Lighthouse budgets for representative routes. | Codex |  |  | Open |  | G-26 | Performance budgets need a named business owner and pre-approved exception path. | Baseline report against approved budgets. | Reliable-runtime gate blocked until closed. | Approve budgets and exception owner. | Product + Engineering
D-28 | Data governance | Approve retention, archival, deletion, erasure, and record-ownership policy. | Treat this as a legal/operational prerequisite to production persistence, not post-launch cleanup. | Codex |  |  | Open |  | G-27 | Data governance must be decided before production records are created. | Approved lifecycle policy and tested data-subject/request workflow. | Reliable-runtime gate blocked until closed. | Approve lifecycle policy and record owners. | Legal + Operations
D-29 | Business continuity | Name the incident commander and approve outage/rollback runbooks and rehearsal cadence. | Rehearse payment, email, database, cloud, and deployment rollback before broad public launch. | Codex |  |  | Open |  | G-28 | Continuity needs ownership and rehearsal, not a static document. | Runbooks plus tabletop/rehearsal evidence and remedial actions. | Reliable-runtime gate blocked until closed. | Name commander and approve rehearsal cadence. | Operations + Engineering
Note on F5: Fill these four columns. Everything to the left is derived and will be overwritten if this workbook is regenerated.

## Assets
Pending Assets
Nothing here exists. Dimensions are what the code actually consumes; where a surface currently renders a generated placeholder, the placeholder is named so you can see what it is standing in for. YELLOW CELLS ARE YOURS.
ID | Category | Asset | Type | Dimensions | Qty | Used by | Currently renders | Status | Owner | Due
A-01 | Brand | Wordmark | SVG | Vector, 1-colour | 1 | Header, footer, favicon | Text 'GC.SYSTEM' | Not supplied
A-02 | Brand | Monogram / favicon | SVG | Square, legible at 16px | 1 | app/icon.tsx | Generated GC monogram from tokens | Not supplied
A-03 | Brand | Brand guidelines PDF | PDF | — | 1 | Partner and press packs | — | Not supplied
A-04 | Property | SlowSpace Coastal · hero | Photo/render | 3200×1800 (16:9), ≥2× retina | 1 | /flow, /collection/[property] | Generated gradient plate, hue 198 | Not supplied
A-05 | Property | SlowSpace Coastal · gallery set | Photo/render | 2400×3000 (4:5) | 8–12 | /gallery, /collection/[property]/gallery | 2 labelled drawings (F-01, F-02) | Not supplied
A-06 | Property | SlowSpace Coastal · site plan | Drawing | Vector or 3000px wide | 1 | /collection/[property]/location | F-02 placeholder | Not supplied
A-07 | Property | SlowSpace Coastal · section drawings | Drawing | Vector | 3–4 | Space surfaces | F-01 placeholder | Not supplied
A-08 | Property | Kyoto House · gallery set | Photo | 2400×3000 (4:5) | 6–10 | /collection/kyoto-house | 1 labelled drawing (F-03) | Not supplied
A-09 | Property | Swiss Vault · gallery set | Photo | 2400×3000 (4:5) | 6–10 | /collection/swiss-vault | 1 labelled drawing (F-04) | Not supplied
A-10 | Property | Oslo Base · gallery set | Photo | 2400×3000 (4:5) | 6–10 | /collection/oslo-base | 1 labelled drawing (F-05) | Not supplied
A-11 | Property | Aerial / context | Photo | 3200×1800 | 1 per property | Location surfaces | — | Not supplied
A-12 | Social | Default share card | PNG | 1200×630 | 1 | app/opengraph-image.tsx | Generated type-only card from tokens | Not supplied
A-13 | Social | Per-property share cards | PNG | 1200×630 | 1 per property | Property routes | Falls back to A-12 | Not supplied
A-14 | Editorial | Journal entry headers | Photo/illustration | 2400×1350 (16:9) | 1 per entry | /journal/[slug] | Gradient plate | Not supplied
A-15 | Editorial | Journal author portraits | Photo | 800×800 | 1 per author | /journal/[slug] | — | Not supplied
A-16 | People | Team portraits | Photo | 1200×1500 (4:5) | 1 per person | /roles/[code] | — | Not supplied
A-17 | Partners | Partner firm logos | SVG | Vector, 1-colour | 1 per firm | /collective/partners | Names withheld until engagements are recorded | Not supplied
A-18 | Diagram | Vehicle / entity structure | SVG | Vector | 1 | /structure, /how-it-works | Text-and-rule diagram | Not supplied
A-19 | Diagram | Waterfall diagram | SVG | Vector | 1 | /how-capital-works | Built in CSS from live figures — arguably better than an asset | Not supplied
A-20 | Document | The Dossier / investment brief | PDF | A4 | 1 | /communique/request | NOTHING. The form promises it and no file exists. | Not supplied
A-21 | Document | Vehicle Agreement template | PDF/DOCX | A4 | 1 per vehicle | Accreditation, settlement | — | Not supplied
A-22 | Press | Press kit | ZIP | — | 1 | /collective/press | Ships empty and says so | Not supplied
A-23 | Video | Property film | MP4 | 1920×1080, ≤60s | 1 per property | Hero surfaces | — | Not supplied
A-24 | Legal | Lawyer-reviewed Terms and Risk Disclosure | Text | — | 1 | content/legal.ts | Unreviewed draft, ~9,000 words | Not supplied

## Domain
The Vehicle Domain Model
EXTRACTED from constants/vehicle-domain.ts (commit b0ade3f), not typed. The LLP sits at the apex; Space, Time and Capital are its constituents; Governance is the constitutional layer that governs the other three — not a fourth business function. Every constituent states what backs it: a ratified object, a UFR field, a derivation, executable code, a REGISTERED gap awaiting a §33 amendment, or OUT OF SCOPE with the reason.
Domain | Section | Constituent | Backing | Backed by | Gap / exclusion detail | Note
Space | What does the LLP own?
| SP.1 · Property | Property Code | object | Property |  | The asset code (PDB-01) is carried on the record today; a dedicated UFR entry is the E-06 gap to close when the field is next touched.
| SP.1 · Property | Property Name | field | UFR-0060 on Property
| SP.1 · Property | Property Type | object | Property |  | Carried on the Property record; the closed type set is an enum question, not a new object.
| SP.1 · Property | Investment Thesis | object | Investment Thesis |  | An attribute of the asset, constitutionally: the thesis names why THIS property. It moved from Intelligence to Space for that reason.
| SP.1 · Property | Asset Status | field | UFR-0066 on Property |  | The lifecycle field. Pre-construction → construction → stabilised → disposition.
| SP.1 · Property | Documents Folder | registered | PropertyDocument | One object per instrument with kind, custody and hash — a folder is not a record.
| SP.2 · Fixed Assets | Furniture & Fixtures | registered | FixedAsset | Asset register entries with cost, life, and depreciation basis. Required before the first fit-out invoice lands.
| SP.2 · Fixed Assets | Plant & Machinery | registered | FixedAsset | Same object, classed plant_machinery.
| SP.2 · Fixed Assets | Renewable Systems | registered | FixedAsset | Same object, classed renewable.
| SP.2 · Fixed Assets | Capital Improvements | registered | FixedAsset | Same object, classed improvement — funded from the Sinking Fund, which is why the class must be distinguishable.
| SP.3 · Asset Protection | Insurance | registered | InsurancePolicy | Policy, insurer, sum insured, expiry. The governance calendar needs the expiry date to fire a compliance event.
| SP.3 · Asset Protection | Valuation | object | Valuation |  | Already ratified. Carries its source and confidence class — a management estimate is not an appraisal.
| SP.4 · Property Documents | Drawings | registered | PropertyDocument | kind: drawing
| SP.4 · Property Documents | Approvals | registered | PropertyDocument | kind: approval. CRZ clearance lives here — the compliance mirror in Governance references it.
| SP.4 · Property Documents | Manuals | registered | PropertyDocument | kind: manual
| SP.4 · Property Documents | Warranties | registered | PropertyDocument | kind: warranty. Expiry-bearing, like insurance — feeds the governance calendar.
| SP.4 · Property Documents | Asset Registers | registered | FixedAsset | The register IS the set of FixedAsset records; a separate register document would be a copy that drifts.
Time | How much time does each LLP Partner legally control?
| TM.1 · Ownership Calendar | Calendar Year | registered | OwnershipCalendar | One record per vehicle per year. The vehicle-level pool the allocations divide.
| TM.1 · Ownership Calendar | Allocation Year | registered | OwnershipCalendar | The year an allocation belongs to — distinct from the calendar year it is used in only once rollover policy exists, which is Decision D-07.
| TM.1 · Ownership Calendar | Available Days | derived | NIGHT_POOL stated per vehicle per year; each position takes floor(pool × stake) |  | The pool is stated for the whole vehicle and each position takes its floor, so the sum of every partner's entitlement can never exceed what the property delivers. Multiplying a per-unit figure would invent nights.
| TM.2 · Allocation Rights | Ownership Percentage | field | UFR-0242 on Ownership Position |  | units_held over total_units_issued. The stake is the input; time is one of its outputs.
| TM.2 · Allocation Rights | Annual Day Allocation | derived | floor(available_days × ownership_percentage) |  | STATIC. It does not vary with usage, season or behaviour — a right attached to ownership, not a reward attached to conduct.
| TM.2 · Allocation Rights | Reserved Days | registered | AllocationRight | Days the vehicle withholds from the pool before division — maintenance closures, statutory closures.
| TM.2 · Allocation Rights | Blackout Rules | registered | AllocationRight | Vehicle-level rules constraining when allocation may be drawn. Rules, never individual draws.
| TM.3 · Usage Rights | Usage Rights | outOfScope |  | Directed out of scope, 1 Aug 2026. Usage is operation, and operation belongs to the Operating Company. The vehicle records who CONTROLS time, never who USED it.
| TM.4 · Calendar Rights | Calendar Rights | outOfScope |  | Directed out of scope, 1 Aug 2026. Same boundary as Usage Rights.
| TM.5 · Time Ledger | Time Ledger | outOfScope |  | Directed out of scope, 1 Aug 2026. A ledger of draws is an operating record. If it is ever pulled inside the vehicle, it enters as a §33 amendment — not as a quiet table.
Capital | What is the financial position of the LLP?
| CP.1 · Investors | Partner Register | object | Investor
| CP.1 · Investors | Ownership Register | object | Ownership Position |  | The same record Time reads its stake from. One register, two domains reading it — never two registers.
| CP.1 · Investors | Capital Accounts | registered | CapitalAccount | Per-partner: contributed, share of profit, drawings, closing balance. The LLP Act requires it and Schedule-form accounts assume it.
| CP.2 · Capital Formation | Investment Offering | object | Investment Offering
| CP.2 · Capital Formation | Commitments | object | Commitment
| CP.2 · Capital Formation | Contributions | object | Investment |  | A settled contribution. The Member Law fires here and nowhere else.
| CP.2 · Capital Formation | Capital Calls | object | Capital Call
| CP.3 · Finance | Debt | registered | DebtFacility | Lender, principal, rate, moratorium, covenants. The ₹5.5 Cr facility currently lives as prose in slowspace.ts — a covenant nobody can query is a covenant nobody monitors.
| CP.3 · Finance | Interest | registered | DebtFacility | Schedule rows on the facility.
| CP.3 · Finance | Repayments | registered | DebtFacility | Schedule rows on the facility.
| CP.3 · Finance | Banking | registered | BankAccount | Account, bank, signatories. Signing authority itself is Governance — the account is Capital, the authority over it is law.
| CP.4 · Revenue | Revenue | registered | LedgerEntry | Recognised revenue, by period and class.
| CP.4 · Revenue | Operating Income | registered | LedgerEntry | class: operating
| CP.4 · Revenue | Brand Income | registered | LedgerEntry | class: brand
| CP.4 · Revenue | Other Income | registered | LedgerEntry | class: other
| CP.5 · Expenses | Operating Costs | registered | LedgerEntry | class: operating_cost
| CP.5 · Expenses | Asset Management | registered | LedgerEntry | class: asset_management
| CP.5 · Expenses | Administration | registered | LedgerEntry | class: administration
| CP.5 · Expenses | Insurance | registered | LedgerEntry | class: insurance — the premium is an expense here; the policy is Space (SP.3).
| CP.5 · Expenses | Professional Fees | registered | LedgerEntry | class: professional_fees
| CP.6 · Reserves | Sinking Fund | code | lib/domain.ts — waterfall stage 4, floor rule F-06 |  | The reserve exists as executable law: 2.5% of revenue in, distribution blocked if paying would breach the floor. A Reserve record joins when persistence exists.
| CP.7 · Valuation | NAV | derived | asset valuations (Space) − debt outstanding + reserves + net working capital |  | Derived, never typed. The prototype carried four different valuations of one house because each screen held its own copy.
| CP.8 · Distribution | Waterfall | code | lib/domain.ts — six stages, closes to 100%, F-05
| CP.8 · Distribution | Debt Service | derived | investor share − partner distribution; stage 5, the senior claim
| CP.8 · Distribution | Partner Distributions | object | Distribution
| CP.8 · Distribution | Retained Earnings | derived | what stage 6 withholds when blocked — retained, never evaporated
| CP.9 · Reporting | Balance Sheet | object | Performance Report |  | Statement kinds on the report object; the statutory filing of them is Governance (Form 8).
| CP.9 · Reporting | Profit & Loss | object | Performance Report
| CP.9 · Reporting | Cash Flow | object | Performance Report
| CP.9 · Reporting | Capital Accounts | registered | CapitalAccount | Reported per partner, per period — same object as CP.1.
| CP.9 · Reporting | Forecasts | object | Forecast |  | Forward-looking, so every figure carries its confidence class.
Governance ⚖ | Under what law does the LLP act, and can it prove compliance?
| GV.1 · LLP Governance | LLP Agreement | object | Agreement |  | The constitutional instrument. Filed as Form 3 within 30 days of incorporation — the statutory mirror row references this record.
| GV.1 · LLP Governance | Partner & Designated Partner Register | object | Investor |  | The register read here is the same Investor set Capital holds — annotated with designated-partner status, never duplicated.
| GV.1 · LLP Governance | Authority Matrix | code | lib/authority.ts — rights, roles, separationViolations() |  | Executable, and checked: no role may hold a dangerous triad. A matrix kept as a document is a matrix nobody enforces.
| GV.1 · LLP Governance | Board / Partner Meeting Records | object | Committee
| GV.1 · LLP Governance | Resolution Register | object | Resolution
| GV.1 · LLP Governance | Voting Register | code | constants/voting.ts — thresholds; ADR-0008 secret ballot, transparent outcome |  | Contribution-weighted per §24a. Ordinary carries above 50% — a tie is not approval. Special at 76%. Tallies are published; who voted how never is.
| GV.1 · LLP Governance | Constitutional Amendments | object | Policy |  | Including §33 amendments — which is how every `registered` candidate in this file becomes real.
| GV.1 · LLP Governance | All Agreements | object | Agreement |  | Operator agreement, brand licence, facility agreement — one object, kinds distinguished. Every contract the vehicle signs lands here or does not bind it.
| GV.2 · Corporate Administration | Incorporation Documents | registered | StatutoryRecord | kind: incorporation — certificate, LLPIN, Form 2.
| GV.2 · Corporate Administration | PAN | registered | StatutoryRecord | kind: pan
| GV.2 · Corporate Administration | TAN | registered | StatutoryRecord | kind: tan — required the day the first salary or contractor payment is made, for TDS.
| GV.2 · Corporate Administration | Registered Office | registered | StatutoryRecord | kind: registered_office. No UFR field carries it today — LLP.office in slowspace.ts is prose. A change of registered office is Form 15; the mirror row exists below.
| GV.2 · Corporate Administration | Statutory Registers | registered | StatutoryRecord | kind: register
| GV.2 · Corporate Administration | Digital Signatures | registered | StatutoryRecord | kind: dsc — every designated partner needs one before any MCA filing can be made.
| GV.2 · Corporate Administration | Banking Authorities | registered | StatutoryRecord | kind: banking_authority — WHO may operate the account. The account itself is Capital (CP.3).
| GV.2 · Corporate Administration | Authorised Signatories | registered | StatutoryRecord | kind: signatory
| GV.2 · Corporate Administration | Enterprise Policies | object | Policy
| GV.2 · Corporate Administration | Governance Calendar | derived | union of every statutory due date below + every expiry-bearing record (insurance, warranties, DSC) |  | Derived from the obligations, never kept by hand. A hand-kept calendar is the one document guaranteed to be wrong the year it matters.
THE STATUTORY MIRROR | Every obligation of an Indian LLP, mapped onto the ComplianceEvent object — the governance calendar is derived from these rows, never kept by hand.
Ref | Instrument | Authority |  | What | Due | Applies when
ST-01 | Form 3 | MCA |  | File the LLP Agreement and any change to it. | Within 30 days of incorporation or of the change | always
ST-02 | Form 11 | MCA |  | Annual Return — partners, contributions, changes in the year. | Within 60 days of financial year end (by 30 May) | always
ST-03 | Form 8 | MCA |  | Statement of Account & Solvency — the accounts CP.9 produces, filed. | By 30 October each year | always
ST-04 | Statutory audit | MCA |  | Audit of the accounts. | Before Form 8 | turnover > ₹40 lakh OR contribution > ₹25 lakh — every GC vehicle crosses the second test at formation
ST-05 | ITR-5 | Income Tax |  | Income tax return of the LLP. | 31 July, or 31 October when audited — GC vehicles are audited, so 31 October | always
ST-06 | TDS returns (24Q/26Q) | Income Tax |  | Quarterly deduction returns against the TAN. | Quarterly | any payment attracting TDS — contractor, professional fees, interest
ST-07 | GST returns | GST |  | Registration and periodic returns. | Monthly/quarterly per registration | taxable supplies exceed the threshold — expected once operations begin
ST-08 | Form 4 | MCA |  | Change of partner or designated partner. | Within 30 days of the change | on every admission, resignation or transfer — every settlement that admits a partner fires this
ST-09 | Form 15 | MCA |  | Change of registered office. | Within 30 days | on relocation
ST-10 | DIR-3 KYC | MCA |  | Annual KYC of every designated partner's DPIN. | By 30 September each year | always
ST-11 | CRZ clearance conditions | State |  | Conditions attached to the Coastal Regulation Zone approval — the approval itself is a Property Document (SP.4). | As conditioned | coastal properties — SlowSpace Coastal is one
§33 AMENDMENT QUEUE | Candidate objects the model needs and the ratified 27 do not contain. Ratifying one moves its constituents from `registered` to `object` without restructuring anything. This is Decision D-18.
| AllocationRight | needed by 2 constituent(s)
| BankAccount | needed by 1 constituent(s)
| CapitalAccount | needed by 2 constituent(s)
| DebtFacility | needed by 3 constituent(s)
| FixedAsset | needed by 5 constituent(s)
| InsurancePolicy | needed by 1 constituent(s)
| LedgerEntry | needed by 9 constituent(s)
| OwnershipCalendar | needed by 2 constituent(s)
| PropertyDocument | needed by 5 constituent(s)
| StatutoryRecord | needed by 8 constituent(s)

## Go-live plan
GETAWAY COLLECTIVE · GO-LIVE LAUNCH PLAN
Decision-led plan · public launch only after every Tier 1 gate is evidenced
ARCHITECTURE |  | PRODUCT |  | PRODUCTION |  | LEGAL / OPS
Mature conceptual system |  | Polished but scaffold-heavy |  | Execution work remains |  | External sign-off required
THE LAUNCH RULE
Do not use public traffic to test identity, money movement, legal terms, or entity facts. A closed pilot may begin only after Tier 1 evidence is complete and all pilot participants are explicitly invited; broad public launch follows the final operational rehearsal and Go/No-Go sign-off.
SEQUENCE — RELATIVE WEEKS, NOT A DATE PROMISE
Phase | Window | Objective | Primary owner | Exit evidence | Blocks | Decision | Status
0 · Lock the boundary | Week 0 | Remove public governance exposure and name accountable owners. | Founders / Legal | Legal review scope, repository visibility decision, entity-verification protocol. | Any public launch | Approve launch scope | Open
1 · Make entry safe | Weeks 1–2 | Authenticate, authorize, rate-limit, and make consent/comms compliant. | Engineering + Legal | End-to-end identity and access tests; consent, unsubscribe, and abuse tests pass. | Pilot | Open invited pilot | Open
2 · Make money real | Weeks 2–4 | Replace static state with a governed data layer and a verified payment path. | Engineering + Finance | Migration, reconciliation, payment success/failure, and audit-event evidence. | Commitments / calls | Enable controlled transactions | Open
3 · Make operations recoverable | Weeks 3–6 | Instrument, secure, deploy predictably, and prove recovery. | Engineering + Operations | Monitoring alerts, rollback drill, restore drill, security and accessibility evidence. | Meaningful external usage | Approve external beta | Open
4 · Complete launch surface | Weeks 5–7 | Close public-facing capability and content gaps without weakening controls. | Product + Brand | Content provenance, notification/PDF paths, scaffold review, approved public inventory. | Broad launch quality | Freeze launch candidate | Open
5 · Rehearse and decide | Week 8 | Run incident, payment, email, and legal-acknowledgement drills; sign Go/No-Go. | Founders + Operations | All Tier 1 rows evidenced; gate owners sign; no unresolved critical incident. | Broad public launch | Go / No-Go | Open
OPERATING CADENCE
Cadence | Attendees | Purpose | Output
Daily launch stand-up | Engineering, Product, Operations | Unblock critical work and surface operational risk. | One owner and next action per red gap.
Weekly gate review | Gate owners + Founders | Review only evidence, exceptions, and decisions. | Signed gate status: Pass / Conditional / Fail.
Launch rehearsal | All accountable functions | Exercise payment, email, outage, rollback, and complaint paths. | Runbook corrections and final Go/No-Go packet.
SOURCE BASIS
Repository evidence: GC-BUILD-STATE.xlsx (1 Aug 2026); authentication currently resolves anonymous, the build-state workbook states database/authentication/payments are absent, and 82 of 135 routes are scaffolds. Architecture/design references confirm strong information architecture, domain modeling, legal acknowledgement patterns, audit intent, motion/brand governance, and accessibility/performance contracts. This plan treats unimplemented runtime controls as launch risk, not a design failure.

## Gates
LAUNCH GAP REGISTER · SINGLE SOURCE OF GO/NO-GO WORK
All rows remain Open until the evidence in column I is reviewed and accepted by the named owner. Tier 1 is non-negotiable for any public launch.
ID | Category | Tier | Workstream | Required outcome | Accountable owner | Gate | Key dependency | Evidence to close | Status
G-01 | Launch Blockers | Tier 1 | Legal | Independent legal review and approved launch document set. | Founders / Legal | G0 | Entity facts | Counsel approval, version register, publication authorization. | Open
G-02 | Launch Blockers | Tier 1 | Governance | Make repository private or remove all legal drafts, identifiers, and internal logic from public access. | Founders / Engineering | G0 | Repository inventory | Access review and written publication policy. | Open
G-03 | Launch Blockers | Tier 1 | Legal | Independently verify every published entity fact. | Legal | G0 | Source documents | Verification log with source, verifier, date, and expiry. | Open
G-04 | Launch Blockers | Tier 1 | Identity | Implement production authentication; protected routes cannot remain anonymous fail-closed. | Engineering | G1 | Identity provider | Sign-in, session expiry, revocation, and protected-route tests. | Open
G-05 | Launch Blockers | Tier 1 | Data | Persist production records; replace static data for commitments and governed operations. | Engineering | G2 | Schema and migration | Production migration, backup, restore, and record lifecycle test. | Open
G-06 | Launch Blockers | Tier 1 | Payments | No commitment/call flow may present until its verified settlement path is live. | Engineering + Finance | G2 | Payment provider | Success, failure, reconciliation, and support reversal runbook. | Open
G-10 | Launch Blockers | Tier 1 | Abuse prevention | Rate-limit public email and form endpoints. | Engineering | G1 | Endpoint inventory | Rate-limit, abuse alert, and rejection-path tests. | Open
G-11 | Launch Blockers | Tier 1 | Compliance | Implement recorded consent, unsubscribe, and marketing compliance. | Legal + Product | G1 | Approved policy | Consent record, preference handling, unsubscribe tests. | Open
G-09 | Platform Readiness | Tier 2 | Error reporting | Configure Sentry or equivalent error capture with ownership and alert routing. | Engineering | G3 | Environment config | Deliberate-error test reaches on-call owner. | Open
G-12 | Platform Readiness | Tier 2 | Delivery | Establish CI/CD with protected deploys and required checks. | Engineering | G3 | Source control policy | Build, tests, preview, approval, and rollback evidence. | Open
G-18 | Platform Readiness | Tier 2 | Release | Verify production deployment and environment separation. | Engineering | G3 | CI/CD | Release checklist, smoke test, and rollback drill. | Open
G-19 | Platform Readiness | Tier 2 | Auditability | Persist immutable audit records for ownership, payment, legal acknowledgement, and document access. | Engineering + Legal | G2 | Data model | Append-only audit record and retrieval test. | Open
G-20 | Platform Readiness | Tier 2 | Authorization | Enforce mature role/right/scope authorization at every sensitive endpoint. | Engineering | G1 | Authentication | Negative authorization tests and periodic access review. | Open
G-22 | Platform Readiness | Tier 2 | Secrets | Establish secret ownership, rotation, expiry, and audit controls. | Engineering + Operations | G3 | Hosting provider | Secret register and rotation exercise. | Open
G-23 | Platform Readiness | Tier 2 | Monitoring | Monitor uptime, API latency, email/payment failures, and database health. | Engineering + Operations | G3 | Production runtime | Dashboards, thresholds, alert routing, weekly review. | Open
G-25 | Platform Readiness | Tier 2 | Security | Complete dependency, OWASP, CSP, header, and independent security review. | Engineering + Security | G3 | Production host | Risk report; critical findings closed or formally accepted. | Open
G-26 | Platform Readiness | Tier 2 | Performance | Set and verify measurable LCP, CLS, INP, bundle, image, and Lighthouse budgets. | Engineering + Product | G3 | Production build | Budget report from representative public and signed-in paths. | Open
G-07 | Product Completeness | Tier 3 | Surfaces | Replace priority registry scaffolds with working user-facing flows. | Product + Engineering | G4 | G1–G3 | Approved route inventory; no public scaffold presented as complete. | Open
G-08 | Product Completeness | Tier 3 | Photography | Publish licensed, consented, and accurately labeled imagery. | Brand + Legal | G4 | Asset register | Asset provenance and labeling review. | Open
G-13 | Product Completeness | Tier 3 | Notifications | Deliver and trace regulated and operational notifications. | Product + Engineering | G4 | G5 + G19 | Delivery records, preferences, and resend/escalation test. | Open
G-14 | Product Completeness | Tier 3 | Documents | Generate and retain correct PDF documents and receipts. | Product + Engineering | G4 | G5 + G19 | Versioned output, retention, retrieval, and sample review. | Open
G-17 | Product Completeness | Tier 3 | Press / Gallery | Ship only verified public content; leave empty states explicit until evidence exists. | Brand + Legal | G4 | G-03 + G-08 | Publication inventory and source approval. | Open
G-15 | Operational Maturity | Tier 4 | Design governance | Reconcile risk taxonomy across registry, UI, legal material, and operations. | Product + Legal | G4 | G-01 | Single approved taxonomy and cross-surface review. | Open
G-16 | Operational Maturity | Tier 4 | Brand governance | Reconcile brand voice across public, transactional, and failure states. | Brand + Product | G4 | Content inventory | Brand review and approved copy register. | Open
G-21 | Operational Maturity | Tier 2 | Disaster recovery | Define backup policy, restore testing, RPO, and RTO. | Operations + Engineering | G3 | G-05 | Approved policy and successful restore drill. | Open
G-24 | Operational Maturity | Tier 2 | Accessibility | Run WCAG, keyboard, screen-reader, and contrast audit on key flows. | Product + Engineering | G4 | Launch candidate | Audit report; critical defects closed or accepted. | Open
G-27 | Operational Maturity | Tier 2 | Data governance | Define retention, archival, deletion, erasure, and record ownership. | Legal + Operations | G3 | G-01 + G-05 | Approved schedule and tested request workflow. | Open
G-28 | Operational Maturity | Tier 2 | Business continuity | Create tested procedures for provider, database, cloud, and rollback outages. | Operations + Engineering | G3 | G-21 + G-23 | Runbooks and recorded tabletop exercise. | Open

## LaunchGates
LAUNCH GATES · DECISION PACKET
Gate | Decision | Minimum evidence | Accountable sign-off | Pass condition | If failed | Status
G0 · Legal boundary | May any public statement or entity fact remain visible? | G-01, G-02, G-03 closed. | Founders / Legal | Approved document set and verified publication inventory. | Remove from public visibility; do not launch. | Open
G1 · Safe entry | May an invited person identify and interact? | G-04, G-10, G-11, G-20 closed. | Engineering + Legal | Authentication, authorization, abuse, and consent tests pass. | No pilot; keep sensitive routes unavailable. | Open
G2 · Governed transaction | May money or ownership data move? | G-05, G-06, G-19 closed. | Engineering + Finance + Legal | Persisted records, settlement/reconciliation, immutable audit evidence. | No commitments, calls, payments, or ownership changes. | Open
G3 · Reliable runtime | May meaningful external usage begin? | G-09, G-12, G-18, G-21, G-22, G-23, G-25, G-26, G-27, G-28 closed. | Engineering + Operations | Monitoring, security, recovery, release, and governance drills pass. | Restrict exposure; remediate before scale. | Open
G4 · Launch candidate | Is the experience complete and trustworthy? | G-07, G-08, G-13, G-14, G-15, G-16, G-17, G-24 closed or formally deferred without regulatory/decision impact. | Product + Brand + Legal | Public inventory, content provenance, accessibility, and design governance approved. | Do not broaden launch; remove incomplete scope. | Open
G5 · Go / No-Go | May the public launch occur? | G0–G4 pass; rehearsal complete; no critical unresolved incident. | Founders | Signed decision packet with scope, support owner, and rollback authority. | Hold launch; set new review date after remediation. | Open
RULE: evidence, not optimism. A gap may be accepted only by the accountable owner, and no Tier 1 exception is compatible with a public launch.

## Enterprise Operating
Getaway Collective — Enterprise Operating Model v2.0
## Operating rule
Getaway Collective is a constitutional capital, governance, and portfolio
platform. It does not become an operating company for hospitality,
construction, engineering, technology, tax, or marketing work.
> Humans make fiduciary decisions. AI manages information. Partner firms execute defined work.
A title, employer, or partner engagement never creates authority. Authority is
always a named, time-bound grant to an identity, with enterprise or LLP scope,
recorded reason, grantor, and review date.
## Constitutional operating platform
```text
GETAWAY COLLECTIVE
Capital · Governance · Portfolio
Shared Chief Executive VP — Portfolio & Platform
Enterprise direction Enterprise integration
┌───────────────┬────────────────┬────────────────┐
│ │ │ │
Investor Office Portfolio Office Governance Office AI Operating Layer
capital relation LLP/asset control constitutional GC-01 / GC-02
integrity
```
### Executive leadership
¦ Constitutional function ¦ Accountable leader ¦ May decide ¦ Must not decide alone ¦
¦ --- ¦ --- ¦ --- ¦ --- ¦
¦ Enterprise direction ¦ Shared Chief Executive ¦ strategy, executive appointment proposals, institutional relationships, Board reporting ¦ resolutions, regulated approvals, or an exception to separation of powers ¦
¦ Enterprise integration ¦ VP — Portfolio & Platform ¦ portfolio cadence, risk escalation, partner coordination, workflow completion ¦ investment approval, financial execution, governance review, or a binding legal position without the required office or resolution ¦
### Internal constitutional functions
¦ Function ¦ Purpose ¦ Core workflow ownership ¦ Existing authority home ¦
¦ --- ¦ --- ¦ --- ¦ --- ¦
¦ Investor Office ¦ capital relations and investor continuity ¦ enquiry, qualification, document collection, meeting preparation, reporting dispatch, escalation ¦ Executive Office plus Compliance Office for explicit acceptance/accreditation grants ¦
¦ Portfolio Office ¦ LLP and portfolio control ¦ vehicle lifecycle, acquisition docket, reserve/debt review, valuation and exit preparation ¦ Investment Committee and Executive Office ¦
¦ Governance Office ¦ constitutional integrity ¦ policy/version register, resolutions, conflicts, statutory calendar, decision register, authority administration ¦ Governance Office, Board, Audit & Risk Committee, Governance & Ethics Committee ¦
¦ AI Operating Layer ¦ information coordination, monitoring, drafting, task routing, and escalation ¦ alerts, board-pack assembly, status synthesis, docket preparation, communications continuity ¦ no fiduciary authority; no constitutional grant capable of approval or execution ¦
## Partner-firm model
Partner firms are capacity umbrellas. They may supply several disciplines under
one engagement, but neither the firm nor a discipline label receives a blanket
constitutional grant.
¦ Partner-firm umbrella ¦ Bundled capability ¦ Constitutional boundary ¦ Typical access posture ¦
¦ --- ¦ --- ¦ --- ¦ --- ¦
¦ Governance & Financial Compliance Partner ¦ chartered accountancy, tax, company-secretarial work, statutory filing coordination, audit liaison ¦ prepares records and filings; does not approve policy, move capital, or resolve governance ¦ vehicle-scoped read/write working-docket access; named personnel may receive `compliance.record` only when required ¦
¦ Legal & Entity Advisory Partner ¦ legal counsel, LLP formation support, contract drafting, regulatory interpretation ¦ advises and drafts; does not publish binding documents or approve a resolution ¦ need-to-know document access; no `content.publish`, `policy.approve`, or `resolution.resolve` grant by default ¦
¦ Portfolio & Technical Advisory Partner ¦ valuation, technical diligence, quantity surveying, architecture, project controls ¦ produces independent evidence; does not approve acquisition, deploy capital, or advance the asset lifecycle ¦ dossier upload/review access restricted to the relevant LLP and work item ¦
¦ Banking, Debt & Insurance Partner ¦ debt advisory, banking coordination, insurance brokerage ¦ obtains quotations and records; does not draw debt, change coverage, or execute distributions ¦ read-only financial evidence and task-specific upload access ¦
¦ Digital Platform Partner ¦ web maintenance, engineering, security monitoring, release work, accessibility and performance remediation ¦ operates approved technical work; has no capital, ownership, compliance, or governance decision right ¦ separate operational access with least privilege, environment separation, expiry, session audit, and emergency revocation ¦
¦ Brand & Communications Partner ¦ public copy production, photography, design production, press coordination ¦ creates materials; cannot put legal or binding content in force ¦ asset/content workspace access; publication remains with the Governance Office or the approved constitutional process ¦
¦ Operating Partner ¦ property and hospitality delivery under approved agreement ¦ executes the contracted operating plan; cannot alter ownership, capital terms, or governance ¦ LLP-scoped operational work queue and document access only ¦
## Access Admin design
The Access Admin must manage six distinct records. It must never grant a
constitutional right to a company record.
1. **Partner firm** — legal entity, capability umbrellas, engagement status,
conflicts, insurance, and contract dates.
2. **Named identity** — a human connected to a partner firm or internal
function, with identity verification and an individual sign-in.
3. **Engagement** — firm-to-enterprise or firm-to-LLP mandate, scope,
deliverables, confidentiality, conflict position, start/end date, and owner.
4. **Constitutional appointment** — an internal office/committee appointment;
this is not interchangeable with employment or a vendor engagement.
5. **Authority grant** — named identity, right, enterprise/LLP scope, grantor,
reason, effective date, expiry, and revocation record.
6. **Workflow assignment** — work item, accountable constitutional function,
executing firm, named assignee, reviewer, decision owner, deadline, and
evidence.
### Access rules
- A partner firm can be engaged across many LLPs; each LLP scope is explicit.
#NAME?
identity; conflicts are assessed before a grant becomes live.
#NAME?
#NAME?
grant has an expiry and review date.
#NAME?
Digital Platform Partner may fix the platform but cannot see or change
capital, ownership, accreditation, legal acknowledgement, or resolution
records unless a separate, narrow, auditable approval is present.
#NAME?
#NAME?
holder may combine investment approval, financial execution, and governance
review.
## Workflow architecture
### 1. Partner onboarding and renewal
`Candidate firm → diligence → conflict disclosure → engagement approval → named personnel → identity verification → scoped access request → separation check → grant → periodic review → renewal or revocation`
**Control points:** Governance Office owns the engagement register; the
requesting constitutional function confirms need; the grantor records reason;
Access Admin rejects a missing LLP scope, missing expiry, or failed separation
check.
### 2. LLP work docket
`GC-01 detects or receives a work item → Portfolio/Governance/Investor Office owns it → executing partner firm receives task → named assignee submits evidence → constitutional reviewer validates → decision owner approves or escalates → immutable record closes`
Examples:
#NAME?
engagement, while each deliverable still has a named CA/CS assignee and a
Governance Office reviewer.
- Website maintenance, security remediation, software release, accessibility,
and performance work flow to one Digital Platform Partner engagement. The
partner completes the task; an internal release owner accepts the evidence;
no partner identity receives capital or governance authority.
### 3. Authority lifecycle
`Request → verify engagement/appointment → define right + scope + expiry → conflict and separation check → grantor approval → session logging → 30-day expiry review → renew, reduce, or revoke`
Required views in Access Admin:
#NAME?
#NAME?
#NAME?
#NAME?
person with assigned work, or a task awaiting a constitutionally authorised
reviewer.
### 4. AI escalation
GC-01 and GC-02 may draft, classify, monitor, route, remind, and assemble
information. They must create an escalation—not an approval—when a matter
involves:
- investment or capital allocation;
- investor accreditation, commitment acceptance, or binding agreement;
#NAME?
matter;
- authority grant/revocation, policy, resolution, conflict, or exception; or
#NAME?
threshold.
The escalation carries source records, a factual summary, proposed next steps,
the required human decision owner, and a deadline. The human outcome is then
written back to the workflow record.
## Build order
1. Keep the current rights-first authority model; do not add a super-admin or
company-level authority.
2. Build **Partner Firms**, **Engagements**, **Named Personnel**, and
**Workflow Assignments** ahead of broad external access.
3. Build the **Access Admin** views for grants, expiries, revocations,
unassigned rights, separation alerts, and LLP scope.
4. Add the Digital Platform Partner operational-access layer separately from
domain authority, with session audit, expiry, environment segregation, and
emergency revocation.
5. Add GC-01 task/exception orchestration first; add GC-02 conversation
continuity only after identity, consent, authorization, and audit controls
are production-ready.
This structure scales to many LLPs because partner firms are reusable capacity
umbrellas, while each decision, grant, task, and escalation stays attached to
the correct constitutional function, named human, and LLP scope.